## STRATEGIC ALIGNMENT
2. ANDA Alignment Criteria
2.1. Vision
“Leading a rapidly growing economy that generates wealth for its people”
2.2 Mission
To facilitate inclusive and innovative socio-economic growth through promoting sustainable enterprises development and implementation of high impact initiatives
2.3 Core Values
Ø Innovation;
Ø Accountability;
Ø Honesty;
Ø Fairness;
Ø Efficiency and effectiveness
The projects in the SDBIP have been crafted such that they are aligned to, and can contribute to the long-term and medium-term strategic planning documents of the District municipality as well as that of the Agency, namely the District Development Plan 2030, ANDM Integrated Strategic Plan (IDP) and Multi Year Business Plan.
DDP | IDP | ANDA
Goal 1: | Goal 2: | Goal 2:
An enabling infrastructure network | Basic Services Delivery and Community Empowerment | Economic Infrastructure Development
Goal 2: | Goal 4: | Goal 4:
Capable Democratic Governance | A capable and Financially viable institution | Good Governance
Goal 3
Effective Public Participation ,Good Governance and Partnerships
Goal 3: | Goal 1: | Goal 1:
An innovative, inclusive and growing economy | Inclusive Growth and Development | Sustainable Inclusive Economic Growth
Goal 3:
Sound Financial Management
Goal 4: | Goal 3: | Goal 4:
Environmental sustainability | Effective Public Participation, Good Governance and Partnerships | Good Governance
Goal 1
Sustainable Inclusive Economic Growth
Goal 5: | Goal 1: | Goal 1:
Rural Development and Innovative and high value agriculture | Inclusive Growth and Development | Sustainable Inclusive Economic Growth
Goal 6: | Goal 4: | Goal 5:
Improved Human Development | A Capable and financial viable institution | Enhancing Human Capabilities

## OVERALL PERFORMANCE
ALFRED NZO DEVELOPMENT AGENCY
ACHIEVED TARGETS VS NOT ACHIEVED BY DEPARTMENT
Unit | Total No. of targets | Achieved | Not Achieved | Achieved% | % Not Achieved
Programmes | 38 | 35 | 3 | 92.11% | 7.895%
Trade & Investment Promotion | 12 | 8 | 4 | 66.67% | 33.33%
Finance and Admin | 47 | 44 | 3 | 93.62% | 6.383%
Office of the Chief Executive Officer | 7 | 4 | 3 | 57.14% | 42.86%
TOTAL | 104 | 91 | 13 | 87.5% | 14.29%
Department | 2023/2024 Mid-term Performance |  |  | 2024/2025 Mid-term Performance |  |  | Improved, Maintained or Declined
| Total No. of Targets | % Achieved | % Not Achieved | Total No. of targets | % Achieved | % Not Achieved | Outcome
Chief Executive Officer | 7 | 100% | 0% | 7 | 57.14% | 57.14%
Programmes | 19 | 63% | 37% | 38 | 92.11% | 7.895%
Trade and Investment | 7 | 86% | 14% | 12 | 66.67% | 33.33%
Finance and Administration | 18 | 94% | 6% | 47 | 93.62% | 6.383%
Overall Percentage | 51 | 82% | 18% | 104 | 87.5% | 14.29%

## FINANCE & ADMIN
3.7.3 FINANCE AND ADMINISTRATION | [6 empty] | Number of targets | Not achieved
Section Name | Supply Chain Management
National KPA | Financial Viability and financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound Financial Management
Business Plan Project | Procurement Projects
Business Plan Reference | 3.7.3.1
Strategic Objective | Maximise economies of scale and value for money by complying with SCM Policies
Baseline | Annual Implementation of SCM policy Reports produced
Annual Output | Four (4) Quartely Implementation of Supply Chain Management Policy Reports dealing with (deviations, irregular expenditure, contract register, orders issued less than R30 000, orders issued less than R200 000, bids awarded above R200 000, updated supplier database, progress with implementation of procurement plan, sitting of bid committees)
Budget Amount | R0.00
Organisational Classification | Supply Chain Management/Procurement Projects
Annual KPI | 4 x Quartely Implementation of Supply Chain Management Policy Reports produced dealing with (deviations, irregular expenditure, contract register, orders issued less than R30 000, orders issued less than R200 000, bids awarded above R200 000, updated supplier database, progress with implementation of procurement plan, sitting of bid committees) by 30 June 2025.
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.1 | 1 | Complete 1 Target: 1.To consolidate and submit to the office of the CEO Quarter 1 Report on implementation of the Supply Chain Management Policy entailing (deviation reports, Irregular expenditure reports,contract register, report of orders issued less than R30 000, reports of orders issued less than R200 000, reports of bids awarded above R200 000, 1 x updated supplier database, 1 x sitting of bid committees report, 1 x progress with implementation of procurement plan) to the Office of the CEO by 30 September 2024 | R 0.00 | POE 1. Quarterly Report on implementation of the Supply Chain Management Policy 2. Proof of submission to office of the CEO | None | N/A
| 2 | Complete 1 Target: 1.Supply Chain Management Policy entailing (deviation reports, Irregular expenditure reports,contract register, report of orders issued less than R30 000, reports of orders issued less than R200 000, reports of bids awarded above R200 000, 1 x updated supplier database, 1 x sitting of bid committees report, 1 x progress with implementation of procurement plan) to the Office of the CEO by 31 December 2024 | R 0.00 | POE 1. Quarter 2 Report on implementation of the Supply Chain Management Policy 2. Proof of submission to the office of the CEO | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: 1.To consolidate and submit to the Office of the CEO Quarter 1 Report for the period ending 30 September 2024 on implementation of the Supply Chain Management Policy entailing (deviation reports, Irregular expenditure reports,contract register, report of orders issued less than R30 000, reports of orders issued less than R200 000, reports of bids awarded above R200 000, 1 x updated supplier database, 1 x sitting of bid committees report, 1 x progress with implementation of procurement plan) 2. To consolidate and submit to the Office of the CEO Quarter 2 Report for the period ending 31 December 2024 on implementation of the Supply Chain Management Policy entailing (deviations reports, irregular expenditure, contract management register, orders issued less than R30 000, orders issued less than R200 000, bids awarded above R200 000, updated supplier database, progress with implementation of procurement plan, sitting of bid committees) | R 0.00 | POE Quarter 1 Report on implementation of the Supply Chain Management Policy entailing (3 x deviation reports, irregular expenditure reports, contract register, report of orders issued less than R30 000, reports of orders issued less than R200 000, reports of bids awarded above R200 000, updated supplier database, sitting of bid committees report, progress with implementation of procurement plan). Quarter 2 Report for the period on implementation of the Supply Chain Management Policy entailing ( deviation reports, Irregular expenditure reports, contract register, report of orders issued less than R30 000, reports of orders issued less than R200 000, reports of bids awarded above R200 000, updated supplier database, Sitting of bid committees report, 1 x progress with implementation of procurement plan) | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Supply Chain Management
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound Financial Management
Business Plan Project | Asset Management
Business Plan Reference | 3.7.3.2
Strategic Objective | Update of Fixed Assets Register and safe guarding & maintenance of assets
Baseline | Twelve (12) Asset Management reports produced
Annual Output | 4X Quartely Asset Management Report produced dealing with fixed asset register, purchase listing (additions), asset verification reports, updates to the portfolio of assets insured by 30 June 2023.
Budget Amount | R0.00
Organisational Classification | Supply Chain Management/Asset Management
Annual KPI | Number of Quartely Asset Management reports produced
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.2 | 1 | Complete 1 Target: 1. To produce Quarter 1 Asset Management Report dealing with: (3 x fixed asset registers (consolidated assets report), 3 x purchase listing report (additions), 1 x fixed asset verification report, 3 x monthly updates to the portfolio of assets insured) by 30 September 2024 | R 0.00 | POE 1. Quarter 1 Asset Management Report | None | N/A
| 2 | Complete 1 Target: 1.To produce Quarter 2 Asset Management Report dealing with: (3 x fixed asset registers (consolidated assets report), 3 x purchase listing report (additions), 1 x fixed asset verification report, 3 x monthly updates to the portfolio of assets insured) by 31 December 2024 | R 0.00 | POE 1. Quarter 2 Asset Management Report | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets : 2 Quartely Asset Management reports by 31 December 2024 dealing each with: (3x Fived Asset Registers) consolidated asset reports 3x purhase lsiting report )addittions, 1 x fixed asset verfication report, 3 x monthly updates to portfolio of assets insured. | R 0.00 | 2 Quartely Asset Management reports by 31 December 2024 dealing each with: (3x Fived Asset Registers) consolidated asset reports 3x purhase lsiting report )addittions, 1 x fixed asset verfication report, 3 x monthly updates to portfolio of assets insured. | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Supply Chain Management
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound Financial Management
Business Plan Project | Fleet Management
Business Plan Reference | 3.7.3.3
Strategic Objective | Safeguarding and maintenance of Assets
Baseline | 4 Fleet Management reports produced
Annual Output | Four (4)Fleet management reports produced by 30 June 2025
Budget Amount | 5000
Organisational Classification | Supply Chain Management /Fleet Management
Annual KPI | Four (4)Fleet management reports produced by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.3 | 1 | Complete 1 Target: 1. 1. Produce one (1) Quartely Fleet Management Report by 30 September 2024. | R 0.00 | POE 1. Fleet Management Report | None | N/A
| 2 | Complete 1 Target: 1. 1. Produce (1) Quartely Fleet Management Report by 31 December 2024. | R 0.00 | POE 1. Fleet Management Report | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: 6 monthly Fleet Management reports produces by 31 December 2024 | R 0.00 | 6 monthly Fleet Management reports produced. | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound financial management
Business Plan Project | Budget & Reporting
Business Plan Reference | 3.7.3.4
Strategic Objective | Prepare accurate and reliable Annual Financial Statements, implement mSCOA budgeting and reporting.
Baseline | 2 budget & reporting reports produced
Annual Output | Twenty (20) compliance report consisting of ( 1 x ANDA set of AFS,12 x Sec 87 reports (budget vs actual expenditure), 1 x Sec 88 Mid-term report, 4 x Quarterly in-year Financial and performance Reports), ANDA 2024/25 Final Budget, ANDA 2024/25 Adjusted Budget) submitted by 30 June 2025
Budget Amount | R 353 334.09
Organizational Classification | Finance/ Budget & Reporting
Annual KPI | Twenty (20) compliance reports produced consisting of ( 1 x ANDA set of AFS,12 x Sec 87 reports (budget vs actual expenditure), 1 x Sec 88 Mid-term report, 4 x Quarterly in-year Financial and performance Reports), ANDA 2024/25 Final Budget, ANDA 2023/24 Adjusted Budget) by 30 June 2025.
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.4 | 1 | Complete 2 Targets: 1. To facilitate submission of 2023/24 AFS to AG by 30 September 2024 2. To Prepare and submit ANDA compliance reports to the office of the CEO entailing ( 3 x Section 87 Reports, Quarter 1 In year Financial and perfomance Report) by 30 September 2024 | 233570.13 | POE 1. GRAP Compliant 2023/24 AFS and proof of submission to AG 2. Compliance Reports 3. Proof of submission | None | N/A
| 2 | Complete 3 Targets: 1. To facilitate submission of Adjusted AFS to AG by 31 December 2024 2. To Prepare and submit ANDA compliance reports to the office of the CEO entailing ( 3 x Section 87 Reports, Quarter 2 In year Financial and perfomance Report) by 31 December 2024 3. To recieve a Draft & final Audit report. | R 0.00 | POE 1. Adjusted AFS and proof of submission to AG 2. Compliance Reports 3. Proof of submission 4. Draft & final Audit report. | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: 1. Submission of 2023/24 AFS 2. 6 x Section 87 Report (budget vs actual expenditure) and submitted no later than 7 working days after the end of each month to the ANDM by 31 Decemberr 2024 3. To prepare Quarter 1 2023-24 In year Financial Reports by 30 Septemebr 2022 4. External Audit 5.To prepare Quarter 2 2023-24 In year Financial Reports by 31 December 2024 | 233570.13 | 1. 2023/24 AFS submitted to the AG 2. Proof of submission of 6 x Section 87 Report (budget vs actual expenditure) no later than 7 working days after the end of each month to the ANDM . 3. Quarter 1 2023-24 In year Financial Reports prepared by 30 Septemebr 2024 4. Audit report 5.Quarter 2 2024-25 In year Financial Reports prepared by 31 December 2024 | 5 Targets Achieved. 0 Target Not Achived |  | 5
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound financial management
Business Plan Project | Financial Information Systems
Business Plan Reference | 3.7.3.5
Strategic Objective | Comply with National Treasury mSCOA regulations
Baseline | mSCOA implementation Plan,(mSCOA Progress Reports), Proof of payment of service fees
Annual Output | Monitoring implementation of one (1) mSCOA Financial Accounting System.
Budget Amount | 2073500
Organizational Classification | Finance/Financial Information Systems
Annual KPI | Four (4) Munsoft Financial System Reports produced by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.5 | 1 | Complete 1 Target: 1. To produce one (1) quartely System Report (GL and TB) by 30 September 2024. | 1212060.38 | POE 1. System Report | None | N/A
| 2 | Complete 1 Target: 1. To produce one (1) quartely System Report (GL and TB) by 31 December 2024. | 86654.69 | POE 1. System Report | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: 1. Two Quartely System Reports generted by 31 December 2024. | 1298715.07 | 1. Two System Reports | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound financial management
Business Plan Project | Improved Audit Opinion
Business Plan Reference | 3.7.3.6
Strategic Objective | Implement revenue and enhancement strategy; improve and maintain expenditure management & controls; strengthen governance and reduce risk; payment of creditors within 30 days
Baseline | Unqualified audit report with no findings
Annual Output | Audit report with no material findings
Budget Amount | 0
Organizational Classification | Finance/Revenue & Expenditure
Annual KPI | Unqualified audit report with no findings
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.6 | 1 | Complete 1 target: 1. To produce 3X deliverable entailing of Investment Reconciliations, 3x PAYE Reconciliationst , 2x VAT reconciliation, 3x Bank Reconciliation Report, 3x Creditors Reconciliation by 30 September 2024. | R 0.00 | POE 1. Reconciliations | None | N/A
| 2 | Complete 1 target: 1. To produce 3X deliverable entailing of Investment Reconciliations, 3x PAYE Reconciliationst , 2x VAT reconciliation, 3x Bank Reconciliation Report, 3x Creditors Reconciliation by 31 December 2024. | R 0.00 | POE 1. Reconciliations 2. Audit report | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: 6X Investment Reconciliations; 6X PAYE Reconciliations; 6X Bank Reconciliations; 6X Creditors Reconciliations; 6X VAT Reconciliations; 6X Employee Costs Reconciliations 6X Grants Reconciliations were prepared and reviewed. | R 0.00 | 6X Investment Reconciliations; 6X PAYE Reconciliations; 6X Bank Reconciliations; 6X Creditors Reconciliations; 6X VAT Reconciliations; 6X Employee Costs Reconciliations 6X Grants Reconciliations prepared and reviewed. | 2 Targets Achieved. 0 Target Not Achived |  | 2
Department | BTO
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | Sound financial management
Business Plan Goal | A Capable and Financially Viable Institution
Business Plan Project | Irregular Expenditure
Business Plan Reference | 3.7.3.7
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Irregular expenditure of R37 193 360 and Fruitless and wasteful expenditure R5 842 774
Annual Output | Four (4) ANDA Irregular Fruitless and Wasteful Expenditure reports by 30 June 2025
Budget Amount | 0
Organisational Classification | Finance/Irregular Fruitless and Wasteful Expenditure
Annual KPI | Unqualified audit report with no findings
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.4.7 | 1 | Complete 1 targets: 1. Submit reports to the Board on Irregular Fruitless and Wasteful expenditures. 2. Recover/investigate fruitless and wastefull expenditure 30 September 2024. | R 0.00 | POE: 1.Irregular Expenditure report | None | N/A
| 2 | Complete 1 targets: 1. Submit reports to the Board on Irregular Fruitless and Wasteful expenditures. 2. Recover/investigate fruitless and wastefull expenditure 31 December 2024. | R 0.00 | POE: 1.Irregular Expenditure report | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: Irregular expenditure - 74% has been investigated and written off. R27 650 951.96 irregular expenditure has been written off by Council and the Balance of R9 542 408.04 is still under investigation. Fruitless and wasteful expenditure : 100% still under investigation | R 0.00 | Board Resolution/Council Resolution / MPAC Report | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | HUMAN RESOURCE MANAGEMENT
National KPA | Municipal Transformation and Organisational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Policy Development
Business Plan Reference | 3.7.2.8
Strategic Objective | Ensure compliant controlled environment
Baseline | Entity approved 2024/2025 Policies
Annual Output | 54 ANDA 2025/2026 Policies reviewed and Submitted to the office of the CEO by 30 June 2025
Budget Amount | R0.00
Organisational Classification | Human Resource Management/Policy Development
Annual KPI | Fifty-four (54) Entity policies reviewed and submitted to the Office of the CEO by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for variance | Corrective Measures
7.2.8 | 1 | Complete 1 target: 1. Monitor implementation of ANDA Policies by 30 September 2024 | 140713.06 | Submit POE: 1. Monitoring Report | None | N/A
| 2 | Complete 1 target: 1. Monitor implementation of ANDA Policies by 31 December 2024 2. Circulate the Policy Review Template to all Departments by 31 December 2024 | 0 | Submit POE: 1. Monitoring Report 2. Consolidated Policy Review Template from all the Departments | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Targets: 1. Implementation on ANDA Policies has been monitored by 31 December 2024 2. Policy Review Template has been circulated to all Departments by 31 December 2024 | 140713.06 | 1. Monitoring Report 2. Consolidated Policy Review Template from all the Departments | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Human Resource Management
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Project | VIP Payroll
Business Plan Reference | 3.7.2.9
Strategic Objective | Efficient and effective payroll system
Baseline | 12 x 2024/2025 Payroll Reports
Annual Output | 12x payroll runs processed, 1x bi-annual Tax return submitted to SARS, 1x annual Tax return submitted to SARS by 30 June 2025
Budget Amount | 11690447
Organisational Classification | Human Resource Management /VIP Payroll
Annual KPI | Twelve(12) payroll run reports prepared and approved by the CEO and 1x bi-annual Tax return and 1x annual Tax returns submitted to SARS by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for variance | Corrective Measures
7.2.9 | 1 | Complete 2 Target: 1.To process 3 payroll runs by 30 September 2024 2. Submit bi-annual Tax return to SARS by 30 June 2023 | 2268841.61 | Submit POE: 1.Payrol Report, EMP201 Report 2. Proof of bi-annual tax return submission | None | N/A
| 2 | Complete 1 Target: 1. To process 3 payroll runs by 31 December 2024 | 2266959.15 | Submit POE: 1. 3 Payrol Report, EMP501 Repor | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed Target: 1. 6 Payroll Runs has been processed 2.Bi-Annual Tax return has been submitted by 31 December 2024 | 4535800.76 | 1.Payrol Report, EMP201 Report 2. Proof of bi-annual tax return submission | 3 Targets Achieved. 0 Target Not Achived |  | 3
Section Name | Human Resource Management
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Staff Establishment Review
Business Plan Reference | 3.7.2.10
Strategic Objective | Ensure Appropriate Organisational Structure to deliver on the Vision of the Strategy
Baseline | 1 x Reviewed and adopted 2024/2025 staff establishment
Annual Output | Reviewed and approved 2025/2026 Staff establishment
Budget Amount | R0.00
Organisational Classification | Human Resource Management/Organogram Review
Annual KPI | One (1) 2025/2026 staff establishment reviewed and approved by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for variance | Corrective Measures
7.2.10 | 1 | Complete 1 Targets: 1. Monitor Implementation of 2024/2025 Staff Establishment by 30 September 2024. | R 0.00 | Submit POE: 1. Report on vacancies filled as per the approved staff establishment | None | None
| 2 | Complete 1 Targets: 1. Monitor Implementation of 2024/2025 Staff Establishment by 31 December 2024 | R 0.00 | Submit POE: 1.Report on vacancies filled as per the approved staff establishement | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Implementation on 2024/2025 Staff Establishment has been monitored by 31 December 2024 | R 0.00 | 1.Report on vacancies filled as per the approved staff establishement | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Human Resource Development
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Skills Development
Business Plan Reference | 3.7.2.11
Strategic Objective | To promote the development of Human Resource Capacity
Baseline | Training and Skills Development Policy
Annual Output | One (1) approved Annual Training Plan 2024/25, training report for trainings conducted and Workplace Skills Plan (WSP) submitted by 30 June 2025
Budget Amount | R0.00
Organisational Classification | Human Resource Development/Skills Development
Annual KPI | One (1) 2024/2025 annaul training plan approved by the CEO, one training on report on training conducted and trainings conducted and one (1) WSP Submitted to LGSETAB , Draft one (1) 2024/2025 Annual Training plan by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly Means of Verifications | Reasons for variance | Corrective Measures
7.2.11 | 1 | Complete 2 Target: 1. Facilitate training as per WSP and ATP by 30 September 2024 2. Attend Quarterly SDF Meeting (Skills Development Forum) by 30 September 2024 | R 0.00 | Submit POE: 1. Registers for trainings conducted 2. Attendance Register for SDF Meetings | Mondatory grant has not yet been deposited into ANDA Account, therefore training could not be completed | Provision will be made on the adjustments budget as the mandatory grant cannot fund the training programme.
| 2 | Complete 3 Target: 1. Coordinate Skills Audit to all employees 2. Develop Draft Annual Training Plan 3. Attend Quarterly SDF Meeting (Skills Development Forum) by 31 December 2024 | R 0.00 | Submit POE: 1. Skills Audit Forms 2. Draft Annual Training Plan 3. Attendance Register for consultation 4. Attendance Register for SDF Meetings
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Training has been facilitated as per WSP and ATP by 30 Sep 2024 2. 2x Quartely SDF meetings has been attended by 31 December 2024 3. 1x Annaul Training Plan has been Developed | R 0.00 | 1. Skills Audit Forms 2. Draft Annual Training Plan 3. Attendance Register for SDF Meetings | 4 Targets Achieved. 1 Target Not Achived
[7 empty] | 4 | 1
Section Name | ICT
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | ICT Management
Business Plan Reference | 3.7.2.12
Strategic Objective | Effective Communication and Information Managaement
Baseline | Hardware and Software with valid Licences
Annual Output | 3 deliverables entailing (Upgrade of anti-virus software on laptops and Monitoring validity of software Licences ) by 30 June 2025
Budget Amount | R0.00
Annual KPI | One (1) Anti-virus software on Laptops renewed, One (1) VIP System license renewed and one (1) server software Licences (munisoft ) renewed by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amounts ( Quarter) | Quarterly Means Of Verifications | Reasons for variance | Corrective Measures
7.2.12 | 1 | None | R 0.00 | None | None | N/A
| 2 | Complete 1 Target: 1. Upgrade of anti-virus software on laptops by 31 December 2024 | R 0.00 | Submit POE: 1.Anti-virus certificate. | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Anti-virus software has been upgraded | R 0.00 | 1.Anti-virus certificate. | 1 Targets Achieved. 0 Target Not Achived
1
Section Name | Administration
National KPA | Municipal Transformation and Organisational Development
IDP Goal | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Records Management
Business Plan Reference | 3.7.2.13
Strategic Objective | To safeguard Organisational memory and Archives
Baseline | 1 manual general filing system developed and implemented
Annual Output | One (1) report on the implementation of Manual general filling system, Establishment and Monitoring of Archives by June 2025
Budget Amount | R0.00
Organisational Classification | Administration/Records Management
Annual KPI | One (1) monitoring report for implementation of one (1) approved manual general filling system and Establishment of Secure Archives by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amounts ( Quarter) | Quarterly Means Of Verifications | Reasons for Varience | Corrective Measures
7.2.13 | 1 | Complete 1 Target: 1.Monitor General Filing System by 30 September 2024 2. Establish secured Archives section by 30 September 2024 | R 0.00 | Submit POE: 1. Draft Manual General filling system 2. Orders for procurement of cabinets | Due to budget constraints, Secured Archives section could not be established | Secured Archives section will be established in the 3rd Qaurter, after the Budget has been adjusted
| 2 | Complete 1 Target: 1. Monitor General Filing System by 31 December 2024 | R 0.00 | Submit POE: 1. Report on implementation of file plan | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. General Filing System has been monitored by 31 December 2024 | R 0.00 | 1. Draft Manual General filling system 2. Attendance Register for the workshop | 2 Targets Achieved. 1 Target Not Achived
[7 empty] | 2 | 1
Section Name | Individual and Institutional Performance Management
National KPA | Municipal Transformation and Organizational development
IDP Goal | A capable and financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Individual Performance Management
Business Plan Reference | 3.7.2.14
Strategic Objective | Improve performance and efficiency level
Baseline | PMS Policy Framework is in place and PMS Workshop was conducted to all employees
Annual Output | 7 x Performance Agreements for Senior Managers and Middle developed and approved, divisional score cards, accountability agreements, performance promises by 30 June 2025
Budget Amount | R0.00
Municipal Classification | IPMS /Performance Management System
Annual KPI | Number of Performance Agreements for Senior Managers and ANDA Staff developed and approved, one Individual PMS workshop conducted to all employees, performance assessement conducted to all entity employees by 30 June 2025.
SDBIP Reference | Quarter | Quarterly Targets | Quartely Budget | Quarterly Means of Verifications | Reasons for Varience | Corrective Measures
7.2.14 | 1 | Complete 3 Targets: 1. Draft and submit 7 individual Performance Agreements and submit to the Office of the CEO by 30 September 2024 2. Update all Individual PMS Templates ( divisional score cards, accountability agreements, performance promises) and submit to all HODs by 30 July 2024. 3. Coordinate submission of Annual Performance Plans by all ANDA Employees by 30 July 2024 | R 0.00 | Submit POE: 1. 4x Signed performance agreements, 2. 3x divisional scorecards, 5x Accountability Agreements, 2x Performance promises 3. 14x Annual Performance Plans | None | None
| 2 | Complete 2 Targets: 1. Coordinate PMS Workshop to all Entity employees by 31 December 2024 2.Cordinates performance reviews for all employees and assesment for all entity employees by 31 December 2024 | R 0.00 | Submit POE: 1.Attendance Register for the PMS Workshop | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. 5x Individual Performance Agreements has been drafted and submitted by 30 September 2024 2.Individual PMS Templates has been updated and submitted by 30 Sep 2024 3. Annual Performance Plans has been submitted by all ANDA Employees 4. PMS Training/Workshop has been coordinated to all employees by 31 December 2024 | R 0.00 | 1. 5x Performance Agreements 2. Divisional scorecards, Accountability Agreements and 3. Attendance Register for PMS Wokshop | 4 Targets Achieved. 1 Target Not Achived |  | 5 | 1
Section Name | Auxilary Services
National KPA | Municipal Transformation and Organisational Development
IDP Goal | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Cleaning Goods and Services
Business Plan Reference | 3.7.2.15
Strategic Objective | Ensure hygiene and clean work environment
Baseline | Cleaning Services
Annual Output | Monitoring of Cleaning Services by 30 June 2025
Budget Amount/Budget | R230 780
Organisational Classification | Auxilary Services/Cleaning Services
Annual KPI | Number of cleaning services monitored by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Quarterly Budget | Quarterly Means Of Verifications | Reasons for Varience | Corrective Measures
7.2.15 | 1 | Complete 1 Targets: 1. Monitor cleaning services by 30 September 2024 | 31600 | Submit POE: 1. Monitoring Register | None | N/A
| 2 | Complete 1 Targets: 1. Monitor cleaning services by 31 December 2024 | 45000 | Submit POE: 1. Monitoring Register | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Cleaning Services has been serviced by 31 December 2024 | 76600 | 1. 2x Monitoring Register | 2 Targets Achieved. 0 Target Not Achived
2
Section Name | Human Resource Management
National KPA | Municipal Transformation and Organizational development
IDP Goal | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Recruitment and Selection
Business Plan Reference | 3.7.2.16
Strategic Objective | Ensure capable workforce to deliver on the Vision of the Strategy
Baseline | 2024/2025 Approved Organisational structure
Annual Output | 6 Vacant positions filled as per 2024/2025 approved Staff Establishment
Budget Amount | R0.00
Organisational Classification | Human Resource Management/Recruitment and Selection
Annual KPI | Number of vacant positions filled as per approved Staff Establishment by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Quarterly Budget | Quarterly Means Of Verifications | Reasons for Varience | Corrective Measures
7.2.16 | 1 | Complete 2 target: 1. Develop and Coordinate approval of the Recruitment Plan and submit to the office of the CEO inline with the budgeted positions on the approved staff establishment by 30 September 2024 2. Coordinate appointment of the 2 Advertised positions (CEO and Manager: Budget, Expenditure and Reporting) | R 0.00 | Submit POE: Recruitment Plan | None | N/A
| 2 | Complete 1 target: 1. Facilitate advertising of 4 vacant positions as per the approved recruitment plan by 31 December 2024 | R 0.00 | Submit POE: Adverts for 4 positions | None | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Recruitment Plan has been developed and submitted by 30 September 2024 2. Appointment of vacant positions as per approved Recruitment Plan and Staff Establishment by 31 December 2024 | R 0.00 | 1. Recruitment Plan 2. Advert for 5 positions 3. Appointment Letter 2 positions | 3 Targets Achieved. 0 Target Not Achived |  | 3
Section Name | Human Resources Management
National KPA | Municipal Transformation and Organizational development
IDP Goal | A capable and financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Occupational Health and Safety
Business Plan Reference | 3.7.2.17
Strategic Objective | Ensure healthy and safety working Environment
Baseline | Approved OHS Policy
Annual Output | Conduct 4x OHS committee meetings, Submit 1 x OHS Action Plan, Submit 1x Assessment Compliance Reports in all respect with the OHSA and the COIDA and the regulations framed under the acts by 30 June 2025
Budget Amount | R0.00
Municipal Classification | OHS /Occupational Helath and Safety
Annual KPI | Number of OHS committes appointed, Number of OHS meeting conducted
SDBIP Reference | Quarter | Quarterly Target | Quartely Budget | Quartelry Means of Verification | Reasons for Varience | Corrective Measures
7.2.17 | 1 | Complete 3 Targets: 1. Coordinate Appointment of OHS Committee members by 30 July 2024 2. Submit 1x Annual OHS Action Plan to the Office of the CEO for approval by 30 September 2024 3. Monitor the sitting of the Health and Safety committee meeting to ensure compliance to OHAS-Act by 30 September 2024 | R 0.00 | Submit POE: 1. Appointment Letter for OHS Committee 2. Approved Annual OHS Action Plan 3. Minutes and Attendance register of the meeting | None | N/A
| 2 | Complete 3 Targets: 1. Monitor the sitting of the Health and Safety committee meeting to ensure compliance to OHAS-Act by 31 December 2024 2. Conduct 1x Assessment Compliance Report on ANDA Building 3. Coordinate Training of OHS Committee members by 31 December 2024 | R 0.00 | Submit POE: 1. Minutes and Attendance register for Health and Safety commitee meeting | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Appointment of OHS Committee Members has been coordinates 2. Annual OHS Action Plan has been drafted and approved 3 Sitting of 2x OHS Committee meetings has been monitored by 31 December 2024. 4. Assessment for Compliance has been conducted | R 0.00 | 1. Appointment Letter for OHS Committee 2. Approved Annual OHS Action Plan 3. 2x Minutes and Attendance register of the meeting | 6 Targets Achieved. 0 Target Not Achived |  | 6
[6 empty] | Total | 47 | 3

## OCEO
[7 empty] | Number of targets | Not achieved
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Sitting of Board Meetings, Monitoring, Evaluation and Reporting
Business Plan Reference | 3.7.4.1
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | 0
Annual Output | 4 Ordinary ANDA Board Meetings, 2 x Special Board Meeting , 1 x Strategic Planning Session and 1x Annual General Meeting (AGM) by 30 June 2025
Budget Amount | R610,000
Organisational Classification | Corporate Governance, Legal Compliance and Services /Sitting of Board Meetings, Monitoring, Evaluation and Reporting
Annual KPI | Number of Ordinary ANDA Board Meetings held, Number of Special ANDA Board Meetings, Number of Strategic Planning Session and number of Annual General Meeting (AGM) by 30 June 2025.
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.4.1 | 1 | Complete 1 Target: 1. Submit Quarter 1 2024/2025 In-Year Performance and Financial Report to ANDM by 30 July 2024 2. Submit quarterly report for period ending 30 June 2024 on implementation of the supply chain management policy to Board by the 30th of September 2024 3. Submit report for period ending 30 June on compliance with the prescribed minimum competency levels to ANDM by the 30th of September 2024 4.CEO to review delegations by the 30th of September 2024 5. Submit 3 Monthly budget statement in prescribed format no later than 7 working days after the end of each month to the ANDM Municipal Manager 6. Submit 1 AFS to board for approval by the 20th of August 2024 7. Submit 1 annual report for year ending 30 June on implementation of the supply chain management policy to Board by 20th August 2024 8.Submit Annual performance report for the period ended 30 June 2024 to ANDM and AG by the 30th of September 2024 9. Submit 1 AFS to AG by the 30th of August 2024 10. Submit AFS to ANDM by 30th of August 2024 | 128510.93 | POE: 1. Attendance Register 2. Meeting Minutes 3.Quarterly Performance Report on the Implementation of Supply Chain Management Policy 4.Annual Report on the implementation of Supply Chain Management Policy 5.Report on Compliance with Prescribed Competency Levels 6. Board Report 7. Delegations Framework 8. 3Monthly Budget Statements 9. Annual Financial Statements 10. Annual Performance Report | None | None
| 2 | Complete 1 Target: 1. Submit 3 Monthly budget statement in prescribed format no later than 7 working days after the end of each month to the ANDM 2. Submit Quarterly Performance and Financial Reporting to ANDA Board by 30th of October 2024 3. Submit quarterly report for period ending 30 September on implementation of the Supply Chain Management policy to Board by 30th October 2024 4. Submit Annual Report to the Board by the 30th of December 2024 5. Submit Annual Report to ANDM by 30 December 2024 6. Hold 1x Annual General Meeting (AGM) | 105312 | POE: 1. 3 Monthly Budget Statements 2. Quarterly Performance and Finance Report 3. Quarterly Report on the Implementation of Supply Chain Management Policy 4. Notice of Annual General Meeting 5. AGM report 6. Meeting Minutes 7. Attendance Register 8. Annual Report 9.Quarterly In-year Performance and Finance Report | The Annual General Meeting (AGM) was not held due to budget constraints | The proposed Annual General Meeting (AGM) will be implemented in quarter 4 after budget adjustments.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Submitted Quarter 1 2024/2025 In-Year Performance and Financial Report to ANDM by 30 July 2024 2. Submitted quarterly report for period ending 30 June 2024 on implementation of the supply chain management policy to Board by the 30th of September 2024 3. Submitted report for period ending 30 June on compliance with the prescribed minimum competency levels to ANDM by the 30th of September 2024 4.CEO to reviewed delegations by the 30th of September 2024 5. Submitted 3 Monthly budget statement in prescribed format no later than 7 working days after the end of each month to the ANDM Municipal Manager 6. Submitted 1 AFS to board for approval by the 20th of August 2024 7. Submitted 1 annual report for year ending 30 June on implementation of the supply chain management policy to Board by 20th August 2024 8.Submitted Annual performance report for the period ended 30 June 2024 to ANDM and AG by the 30th of September 2024 9. Submitted 1 AFS to AG by the 30th of August 2024 10. Submitted AFS to ANDM by 30th of August 2024 11. Submitted 3 Monthly budget statement in prescribed format no later than 7 working days after the end of each month to the ANDM 12. Submitted Quarterly Performance and Financial Reporting to ANDA Board by 30th of October 2024 13. Submitted quarterly report for period ending 30 September on implementation of the Supply Chain Management policy to Board by 30th October 2024 14. Submitted Annual Report to the Board by the 30th of December 2024 15. Submitted Annual Report to ANDM by 30 December 2024 | 233822.93 | 1. Attendance Register 2. Meeting Minutes 3.Quarterly Performance Report on the Implementation of Supply Chain Management Policy 4.Annual Report on the implementation of Supply Chain Management Policy 5.Report on Compliance with Prescribed Competency Levels 6. Board Report 7. Delegations Framework 8. 3Monthly Budget Statements 9. Annual Financial Statements 10. Annual Performance Report | 1 Targets Achieved. 1 Target Not Achived |  | 1 | 1
Section Name | Office of the Chief Executive Officer
National KPA | Communications
IDP Goal | Good governance and public participation
Business Plan Goal | Good Governance
Business Plan Project | Communications project
Business Plan Reference | 3.7.4.2
Strategic Objective | Promotion of stakeholders realations and positive public image of ANDA
Baseline | Draft ANDA Communications and Marketing Strategy
Annual Output | 4x District Communications Forum (DCF) Meetings attended and Develop Communications Strategy by 30 June 2025.
Budget Amount | R0.00
Organisational Classification | Communications
Annual KPI | Number of District Communications Forum (DCF) Meeting attended and number of Communications Strategy develop by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.4.2 | 1 | Complete 1 target : 1. To attend DCF Meeting by 30 September 2024 | R0.00 | 1.Attendance Register for DCF Meetings | None | None
| 2 | Complete 1 target: 1. To attend DCF Meeting by 31 December 2024 | R0.00 | 1.Attendance Register for DCF Meetings | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 2 targets : 1. Attended DCF Meeting by 30 September 2024 2. Attended DCF Meeting by 31 Deecember 2024 | R0.00 | 1.Attendance Register for DCF Meetings | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Individual and Institutional Performance Management
National KPA | Good Governance and Public Participation
IDP Goal | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Institutional Performance Management
Business Plan Reference | 3.7.4.3
Strategic Objective | To strengthen institutional reporting, compliance and performance level
Baseline | 0
Annual Output | 4 Quarterly Performance and financial reports, 1x Annual Performance Report, 1x Midterm Performance Report , 1x Annual Report and 12x monthly management meetings submitted by 30 June 2025
Budget Amount | R 0,00
Organisational Classification | IIPM/Planning and Reporting
Annual KPI | Number of Quartely Performance and Financial reports, Number of Annual Performance Report, Number of Annual Report , Number of monthly management meetings and Number of Midterm Performance Report submitted to the Board by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.4.3 | 1 | Complete 1 Target: 1. Consolidate and Review Q1 in year Performance and Financial Report by 30th of September 2024 2. Consolidate and Review Annual Perfomance Report by 30th of September 2024. 3. Hold 3x Monthly Management Meeting by 30 September 2024 | R0.00 | Submit POE: 1. Proof of submissions to APC, Board and ANDM | None | None
| 2 | Complete 1 Target: 1. Consolidate and Review Q2 in year Performance and Financial Report by 31 December 2024 2. Consolidate and Submit Annual Report by 15 December 2024 3.Hold 3x Monthly Management Meeting by 31 December 2024 | R0.00 | Submit POE: 1. Proof of submissions to APC, Board and ANDM | The Office of the CEO was unable to submit the Q2 Performance report to the APC due to expired shared services of ANDM Audit & Performance Committee with ANDA. | ANDA is in engagement with ANDM with regards to renewing the shared srvices.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Consolidated and Reviewed Q1 in year Performance and Financial Report by 30th of September 2024 2. Consolidated and Reviewed Annual Perfomance Report by 30th of September 2024. 3. Held 3x Monthly Management Meeting by 30 September 2024 4. Consolidated and Reviewed Q2 in year Performance and Financial Report by 31 December 2024 2. Consolidated and Submitted Annual Report by 15 December 2024 3.Held 3x Monthly Management Meeting by 31 December 2024 | R0.00 | 1. Proof of submissions to APC, Board and ANDM | 1 Targets Achieved. 1 Target Not Achived |  | 1 | 1
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Internal Audit
Business Plan Reference | 3.7.4.4
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Reviewed ANDA Audit Action Plan
Annual Output | 1x Reviewed ANDA Audit Action Plan, 4 Quarterly Performance and financial reports, 1x Annual Performance Report, 1x Midterm Performance Report , 1x Annual Report ,, 1x SDBIP , 1x Adjusted SDBIP, 1x MYBP and 1x Adjusted MYBP reviewed by Internal Audit by 30 June 2025
Budget Amount | R0
Organisational Classification | Corporate Governance and Legal Compliance /Internal Audit
Annual KPI | Number of ANDA Audit Action Plan, Quarterly Performance and financial reports, Annual Performance Report, Midterm Performance Report , Annual Report, SDBIP and Multi-Year Business Plan reviewed by Internal Audit by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.4.4 | 1 | Complete 1 Target: 1. Review Audit Action Plan by 30th September 2024 2. Submit Audit Action Plan to Audit Committee by 30th September 2024 3.Submit Reviewed Audit Action Plan to Board by 30th September 2024 4. Review and Audit Institutional Performance reports (1x Annual Performance Report and 1x Quarter 4 Performance and financial reports) by 30 September 2024 | R0.00 | POE: 1. Proof of Performance reports and Audit Action Plan submitted to the Board 2. Proof of Performance reports and Audit Action Plan submitted to APC 3. Reviewed Audit Action Plan | None | None
| 2 | Complete 1 Target: 1. Review Audit Action Plan by 31 December 2024 2. Submit Audit Action Plan to Audit Committee by 31 December 2024 3.Submit Reviewed Audit Action Plan to Board by 31 December 2024 4. Review and Audit Institutional Performance reports (1x Quarter 2 Performance and financial reports) by 31 December 2024 | R0.00 | POE: 1. Proof of Performance reports and Audit Action Plan submitted to the Board 2. Proof of Performance reports and Audit Action Plan submitted to APC 3. Reviewed Audit Action Plan | The Office of the CEO was unable to submit the Audit Action Plan to the APC due to expired shared services of ANDM Audit & Performance Committee with ANDA. | ANDA is in engagement with ANDM with regards to renewing the shared services.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Reviewed Audit Action Plan by 30th September 2024 2. Submitted Audit Action Plan to Audit Committee by 30th September 2024 3.Submitted Reviewed Audit Action Plan to Board by 30th September 2024 4. Reviewed Audit Action Plan by 31st December 2024 5. SubmittedAudit Action Plan to Audit Committee by 31st December 2024 6.Submitted Reviewed Audit Action Plan to Board by 31st December 2024 | R0.00 |  | 1 Target Achieved. 1 Target Not Achived |  | 2 | 1
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Risk Management
Business Plan Reference | 3.7.4.5
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Updated Risk Register
Annual Output | 4x Reviewed ANDA Risk Register by 30 June 2025
Budget Amount | R0.00
Organisational Classification | Corporate Governance and Legal Compliance /Risk Management
Annual KPI | Number of quartely reviews undertaken by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.4.5 | 1 | Complete 1 Target: 1. Review Risk Register by 30th September 2024 2. Submit Risk Register to Audit Committee by 30th September 2024 3.Submit Reviewed Risk Register to Board by 30th September 2024 | R0.00 | POE: 1. Proof of submission to the Board 2. Proof of submission to APC 3. Reviewed Risk Register | Office of the CEO was unable to submitt the Risk Register due to the expiry of the shared services of ANDM Audit Performance Commitee(APC) with ANDA. | ANDA is in engagement with ANDM with regards to renewing the shared services.
| 2 | Complete 1 Target: 1. Review Risk Register by 30th September 2024 2. Submit Risk Register to Audit Committee by 30th September 2024 3.Submit Reviewed Risk Register to Board by 30th September 2024 | R0.00 | POE: 1. Proof of submission to the Board 2. Proof of submission to APC 3. Reviewed Risk Register | The Office of the CEO was unable to submit the Risk Register to the APC due to expired shared services of ANDM Audit & Performance Committee with ANDA. | ANDA is in engagement with ANDM with regards to renewing the shared services.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Reviewed Risk Register by 30th September 2024 2. Submitted Risk Register to Audit Committee by 30th September 2024 3.Submitted Reviewed Risk Register to Board by 30th September 2024 4. Reviewed Risk Register by 31st December 2024 5. Submitted Risk Register to Audit Committee by 31st December 2024 6.Submitted Reviewed Risk Register to Board by 31st December 2024 | R0.00 | 1. Proof of submissions to the Board 2. Proof of submissions to APC 3. Reviewed Risk Registers | 1 Target Achieved. 1 Targets Not Achived |  | 2 | 1
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Legal Services
Business Plan Reference | 3.7.4.6
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | 0
Annual Output | 4x Reviewed ANDA litigations Register by 30 June 2025
Budget Amount | 400000
Organisational Classification | Corporate Governance and Legal Compliance/Legal Services
Annual KPI | Number of quarterly reviews undertaken by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.4.6 | 1 | Complete 1 Target: 1. Review Litgations Register by 30th September 2024 2. Submit Litigations Register to Audit Committee by 30th September 2024 3.Submit Reviewed Litigations Register to Board by 30th September 2024 | 199051.94 | POE: 1. Proof of submission to the Board 2. Proof of submission to APC 3. Reviewed Litigations Register | None | None
| 2 | Complete 1 Target: 1. Review Litigations Register by 31 December 2024 2. Submit Litigations Register to Audit Committee by 31 December 2024 3.Submit Reviewed Litigations Register to Board by 31 December 2024 | 137491.4 | POE: 1. Proof of submission to the Board 2. Proof of submission to APC 3. Reviewed Litigations Register | The Office of the CEO was unable to submit the Litigations Register to the APC due to expired shared services of ANDM Audit & Performance Committee with ANDA. | ANDA is in engagement with ANDM with regards to renewing the shared services.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Reviewed Litigations Register by 30th September 2024 2. Submitted Litigations Register to Audit Committee by 30th September 2024 3.Submitted Reviewed Litigations Register to Board by 30th September 2024 4. Reviewed Litigations Register by 31st December 2024 5. Submitted Litigations Register to Audit Committee by 31st December 2024 6.Submitted Reviewed Litigations Register to Board by 31st December 2024 | 336543.34 | 1. Proof of submission to the Board 2. Proof of submission to APC 3. Reviewed Litigations Register | 1 Target Achieved. 1 Targets Not Achived |  | 2 | 1
[6 empty] | Total | 7 | 3

## PROGRAMMES
3.7.1 PROGRAMMES DEPARTMENT | [6 empty] | Number of targets | Not achived
Department | Programme
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Economic Growth and Development
Business Plan Goal | 1. Sustainable inclusive economic growth 2.Economic infrastructure development
Business Plan Project | Sheep Farming Programme
Business Plan Reference | 3.7.1.1
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | Sheep shearing equipment procured and supplied
Annual Output | 2x Sheep shearing sheds constructed and 1xSheep shearing shed refurbished
Budge Amount | R 1 800 000.00
Organisational Classification | Agriculture, Agro-processing and Forestry/Sheep Farming Programme
Annual KPI | Number of Sheep shearing sheds constructed and refurbished in WMM LM, Umzimvubu and Matatiele by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.1 | 1 | Complete 1 Target: 1. Facilitate the advertisement of 3x Service Providers by 30 September 2024 | R0.00 | 1. Advert. 2. Terms of Reference | None | None
| 2 | Complete 1 Target: 1. Facilitate the appointment of 3x service providers for the construction of 2 shearing sheds and refurbishment of 1 shearing shed by 30 December 2024. | R0.00 | 1. Appointment letters X 3
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Advertisement of 3x Service Providers was facilitated by 30 September 2024 2. Appointment of 3x service providers for the construction of 2 shearing sheds and refurbishment of 1 shearing shed was facilitated by 30 December 2024. | R0.00 | 1. Appointment letters X 3 2. Advert. 3. Terms of Reference | 2 Targets achieved, 0 Targets not achieved |  | 2
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | FRESH PRODUCE INDUSTRY DEVELOPMENT
Business Plan Reference | 3.7.1.2
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | 1x Trade Fair event hosted at Winnie Madikizela Mandela LM
Annual Output | 2 x Trade fairs held by June 2025
Budget Amount | R 500 000.00
Organisational Classification | Enterprise Development and support services / FRESH PRODUCE INDUSTRY DEVELOPMENT
Annual KPI | Number of Trade Fair hosted by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.2 | 1 | Complete 1 Target: 1. Develop and facilitate approval of Concept document by 30 September 2024 2.Stakeholder Engagement by 30 September 2024. | 0 | 1. Concept note. 2. Stakeholder Engagement Reports | None | None
| 2 | Complete 1 Target: 1. Host trade fair at Matatiele by 31 December 2024 | 56780 | 1. Trade Fair Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. The Concept document for Trade Fair was developed and approved by 30 September 2024 2.Stakeholder Engagement was undertaken by 30 September 2024. 3. Trade fair was hosted at Matatiele by 31 December 2024 | 56780 | 1. Concept note. 2. Stakeholder Engagement Reports 3. Trade Fair Report | 2 Targets achieved,0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Emfundisweni Skills Development Centre: Business Support
Business Plan Reference | 3.7.1.3
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | R700 000 financial support provided
Annual Output | R740 000.00 financial support provided by 30 June 2025
Budget Amount | R 600 000.00
Organisational Classification | Enterprise Development and support services /Emfundisweni Skills Development Centre: Business Support
Annual KPI | Amount of R600 000.00 provided for Emfundisweni operational cost by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.3 | 1 | Complete 1 Target: 1. Provide financial support to Emfundisweni Skills Centre for operations by 30 September 2024 2. Facilitate the signing of the SLA with Emfundisweni PAC by 30 September 2024 3. Review Terms of Reference for Emfundisweni PAC by 30 September 2024 | 135033.2 | 1. Proof of payment 2. Signed SLA 3. Reviewed TORs | None | None
| 2 | Complete 1 Target: 1. Monitor operations by December 2024 2. Provide financial support to Emfundisweni Skills Centre for operations by 30 December 2024 | 120845.09 | 1. Monitoring report 2. 3x Proof of payment
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Financial support was provided to Emfundisweni Skills Centre for operations by 30 September 2024 2. Signing of the SLA with Emfundisweni PAC was facilitated by 30 September 2024 3. Terms of Reference for Emfundisweni PAC was reviewed by 30 September 2024 4. Operations were monitored by December 2024 5. Financial support was provided to Emfundisweni Skills Centre for operations by 30 December 2024 | 255878.29 | 1. Proof of payment 2. Signed SLA 3. Reviewed TORs 4. Monitoring report 5. 3x Proof of payment | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Enterprise Development
Business Plan Reference | 3.7.1.4
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed.
Baseline | None
Annual Output | 4x SMMEs provided with non financial support
Budget Amount | R0.00
Organisational Classification | Enterprise Development and support services / Enterprise Development
Annual KPI | Number of SMMEs provided with non financial support by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.4 | 1 | Completed 1 Target: 1. Facilitate non-financial support to 1 xSMMEs by 30 Septermber 2024 | R0.00 | 1. Referral Letters | None | None
| 2 | Completed 1 Target: 1. Facilitate non-financial support to 1 xSMMEs by December 2024 | R0.00 | 1. Referral Letters
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Non-financial support to 1 xSMMEs was facilitated by 30 Septermber 2024 1. Non-financial support to 1 xSMMEs was facilitated by December 2024 | R0.00 | 2x Refferral Letters | 2 Targets achieved, 0 Target not achieved |  | 2 | 1
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | SETA accreditation
Business Plan Reference | 3.7.1.5
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x full SETA accreditation secured by 30 June 2025
Budget Amount | R 200 000.00
Organisational Classification | Enterprise Development and support services /SETA accreditation
Annual KPI | Number of accreditations secured by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5 | 1 | Completed 1 Target: 1. Undertake desktop research on SETA accreditation application requirements by 30 September 2024 2. Develop Terms of Reference by 30 September 2024 | R0.00 | 1.Desktop research report 2. Approved Terms of Reference | The project has been discontinued due to budget constraints | The project will be taken out of the SDBIP in the Midterm Budget adjustment
| 2 | Completed 1 Target: 1. Facilitate the appointment of Service Provider by 30 December 2024 2. . Monitor the progress of accreditation application by 30 December 2024 | R0.00 | 1. Appointment letter 2. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Desktop research on SETA accreditation application requirements was undertaken by 30 September 2024 2. Terms of Reference could not be developed by 30 September 2024 1. The appointment of Service Provider was not facilitated by 30 December 2024 2. . Progress of accreditation application was not monitored by 30 December 2024 | R0.00 | None | 0 Targets achieved, 2 Targets not achieved |  | 2 | 2
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Foodbev: Leanership Programme
Business Plan Reference | 3.7.1.5.1
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1X learnership programme implemented for 80 participants on Bread and Flour Confectionery Baking
Budget Amount | R 5 360 000.00
Organisational Classification | Enterprise Development and support services /Foodbev: Leanership Programme
Annual KPI | Number of leaners on 1x Learnership programme (Foodbev) by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.1 | 1 | Completed 1 Target: 1.Facilitate recruitment of 80 learners by 30 September 2024 2.Commence the implementation 1 learnership Programme by 30 September 2024 | 497950 | 1.Advert 2. Recruitment Report 3. Inception and Induction Report | None | None
| 2 | Completed 1 Target: 1. Monitor the implementation of 1 learnership programme by 30 December 2024 | 1332375 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Recruitment of 80 learners was facilitated by 30 September 2024 2.Implementation 1 learnership Programme commenced by 30 September 2024 3.Implementation of 1 learnership programme was monitored by 30 December 2024 | 1830325 | 1.Advert 2. Recruitment Report 3. Inception and Induction Report 4. Progress Report | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Leanership Programme Local Economic Development
Business Plan Reference | 3.7.1.5.2
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 20 leaners in economic development (LGSETA)
Budget Amount | R440 000.00
Organisational Classification | Enterprise Development and support services /Services SETA: Leanership Programme economic development (LGSETA)
Annual KPI | Number of certificates issued for leaners in 1x Learnership programme economic development (LGSETA) by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.2 | 1 | Completed 1 Target: 1.Commence the implementation 1 learnership Programme of the by 30 September 2024 | 0 | 1. Inception and induction report | None | None
| 2 | Completed 1 Target: 1. Monitor progress implementation of 1 learnership programme by 30 December 2024 | 0 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Implementation 1 learnership Programme commenced by 30 September 2024 2. Progress on implementation of 1 learnership programme was monitored by 30 December 2024 | 0 | 1. Inception and induction report 2. Progress Report | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA : Leanership Programme enviromental practice
Business Plan Reference | 3.7.1.5.3
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 20 employed leaners on environmental practise
Budget Amount | R440 000.00
Organisational Classification | Enterprise Development and support services / LGSETA : Leanership Programme enviromental practice
Annual KPI | Number of leaners in 1x Learnership programmes (LGSETA) by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.3 | 1 | Completed 1 Target: 1.Commence the implementation 1 learnership Programme of the by 30 September 2024 | 0 | 1. Inception and induction report | None | None
| 2 | Completed 1 Target: 1. Monitor progress on implementation of 1 learnership programme by 30 December 2024 | 0 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Implementation 1 learnership Programme commenced by 30 September 2024 2. Progress on implementation of 1 learnership programme monitored by 30 December 2024 | 0 | 1. Inception and induction report 2. Progress Report | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Artisan Recognition of Prior Learning(ARPL) on Plumbing
Business Plan Reference | 3.7.1.5.4
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x ARPL programmes implemented for 48 employed leaners on plumbing
Budget Amount | R1 750 000.00
Organisational Classification | Enterprise Development and support services / LGSETA: ARPL on Plumbing
Annual KPI | Number of leaners in 1x ARPL programme (LGSETA) by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.4 | 1 | Completed 1 Target: 1. Commence the implementation 1 ARPL Programme of the by 30 September 2024 | 161875 | 1. Inception and induction report | None | None
| 2 | Completed 1 Target: 1. Monitor progress on implementation of 1 ARPL programme by 30 December 2024 | 0 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Implementation 1 ARPL Programme commenced by 30 September 2024 1. Progress on implementation of 1 ARPL programme was monitored by 30 December 2024 | 161875 |  | 2 Targets achieved,0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Artisan Recognition of Prior Learning(ARPL) Programme (bricklaying)
Business Plan Reference | 3.7.1.5.5
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x ARPL programmes implemented for 49 employed leaners on Bricklaying
Budget Amount | R1 750 000.00
Organisational Classification | Enterprise Development and support services / LGSETA: ARPL on Bricklaying
Annual KPI | Number of leaners in 1x ARPL programme by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.5 | 1 | Complete 1 Target : 1.Commence the implementation 1 ARPL Programme of the by 30 September 2024 | 152162.5 | Inception and induction report | None | None
| 2 | Completed 1 Target: 1. Monitor progress implementation of 1 ARPL programme by 30 December 2024 | 0 | Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Implementation 1 ARPL Programme of the by 30 September 2024 2. Progress on implementation of 1 ARPL programme by 30 December 2024 | 152162.5 | Inception and induction report Progress Report | 2 Targets achieved,0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA Apprenticeship Programme (Plumbing)
Business Plan Reference | 3.7.1.5.6
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 06 employed leaners on plumbing
Budget Amount | R589 734.00
Organisational Classification | Enterprise Development and support services / LGSETA: Apprenticeship on plumbing
Annual KPI | Number of leaners in 1x Apprenticeship programme by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
.7.1.5.6 | 1 | Complete 1 Target : 1.Commence the implementation 1 apprenticeship Programme of the by 30 September 2024 | 45458.64 | 1. Inception and induction report | None | None
| 2 | Completed 1 Target: 1. Monitor progress on implementation of 1 apprenticeship programme by 30 December 2024 | 0 | Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Commence the implementation 1 apprenticeship Programme of the by 30 September 2024 2. Monitor progress on implementation of 1 apprenticeship programme by 30 December 2024 | 45458.64 | 1. Inception and induction report 2. Progress Report | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Apprenticeship Programme (Plumbing)
Business Plan Reference | 3.7.1.5.7
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 14 Unemployed leaners on plumbing
Budget Amount | R3 140 046.00
Organisational Classification | Enterprise Development and support services / LGSETA: Apprenticeship on plumbing
Annual KPI | Number of leaners in 1x Apprenticeship programme by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.7 | 1 | Complete 1 Target : 1.Commence the implementation 1 apprenticeship Programme of the by 30 September 2024 | 106070.22 | 1. Inception and induction report | None | None
| 2 | Completed 1 Target: 1. Monitor progress implementation of 1 apprenticeship programme by 30 December 2024 | 0 | Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Commence the implementation 1 apprenticeship Programme of the by 30 September 2024 2. Monitor progress implementation of 1 apprenticeship programme by 30 December 2024 | 106070.22 | 1. Inception and induction report Progress Report | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA: Learnership (Generic Management)
Business Plan Reference | 3.7.1.5.8
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 30 Unemployed leaners on generic Management
Budget Amount | R 1 126 164.38
Organisational Classification | Enterprise Development and support services / Services SETA: Learnership (Generic Management)
Annual KPI | Number of leaners in 1x Learnership programme by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.8 | 1 | Complete 1 Target : 1. Monitor progress implementation of 1 learnership programme by 30 September 2024 | 116820 | 1. Progress Report | None | None
| 2 | Completed 1 Target: 1. Monitor progress implementation of 1 learnership programme by 30 December 2024 2. Facilitate the assessment and moderation by 30 December 2024 | 59400 | 1. Progress Report 2. Assessment & Moderation Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress implementation of 1 learnership programme by 30 September 2024 2. Monitor progress implementation of 1 learnership programme by 30 December 2024 3. Facilitate the assessment and moderation by 30 December 2024 | 176220 | 1. Progress Report 2. Assessment & Moderation Report 3. Progress Report | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA : Leanership Programme(Business Administration Services)
Business Plan Reference | 3.7.1.5.9
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 49 leaners in Business Administration Services
Budget Amount | R 1 473 062.50
Organisational Classification | Enterprise Development and support services / Services SETA : Leanership Programme( Business Administration Services)
Annual KPI | Number of certificates issued for leaners in 1x Learnership programmes (Business Administration Services) by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.9 | 1 | Complete 1 Target : 1. Monitor progress on implementation of 1 learnership programme in Business Admin Services for 49 learners by 30 September 2024 | 273240 | 1. Progress Report | None | None
| 2 | Complete 1 target: 1. Monitor progress on implementation of 1 learnership programme in Business Admin Services for 49 learners by 30 December 2024 | 745480 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress on implementation of 1 learnership programme in Business Admin Services for 49 learners by 30 September 2024 2. Monitor progress on implementation of 1 learnership programme in Business Admin Services for 49 learners by 30 December 2024 | 1018720 | 1. 2x Progress Reports | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA : Leanership Programme (Sewing)
Business Plan Reference | 3.7.1.5.10
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 14 leaners
Budget Amount | R 682 500.00
Organisational Classification | Enterprise Development and support services / Services SETA : Leanership Programme (Sewing)
Annual KPI | Number of certificates issued for leaners in 1x Learnership programmes by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.10 | 1 | Complete 1 Target : 1. Monitor progress on implementation of 1 learnership programme for 30 learners on Sewing by 30 September 2024 2. Facilitate assessment and moderation by 30 September 2024 | 145530 | 1. Monitoring Report 2. Assessment and Moderation Report | None | None
| 2 | Complete 1 Target: 1. Facilitate the close up of the project by 30 December 2024 | 267300 | 1. Close up report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress on implementation of 1 learnership programme for 30 learners on Sewing by 30 September 2024 2. Facilitate assessment and moderation by 30 September 2024 3. Facilitate the close up of the project by 30 December 2024 | 412830 | 1. Monitoring Report 2. Assessment and Moderation Report 3. Close up report | 2 Targets achieved,0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA: NATED internship programme
Business Plan Reference | 3.7.1.5.11
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Nated internship Programme for 70 unemployed learners implemented.
Budget Amount | R 787 295.25
Organisational Classification | Enterprise Development and support services / Services SETA: NATED internship programme
Annual KPI | One (1) NATED Internship programme implemented for 70 learners by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.11 | 1 | Complete 1 Target : 1. Monitor progress on implementation NATED Internship Programme by 30 September 2024 | 356400 | 1. Progress Report | None | None
| 2 | Complete 1 Target: 1. Monitor progress on implementation NATED Internship Programme by 30 December 2024 | 709830 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress on implementation NATED Internship Programme by 30 September 2024 2. Monitor progress on implementation NATED Internship Programme by 30 December 2024 | 1066230 | 1. 2x Progress Reports | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA: Vocational Internship Programme
Business Plan Reference | 3.7.1.5.12
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x vocational internship Programme for 76 unemployed learners implemented.
Budget Amount | R556 273.45
Organisational Classification | Enterprise Development and support services / Services SETA: Vocational Internship Programme
Annual KPI | One (1) Vocational Internship programme implemented for 76 learners by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.12 | 1 | Complete 1 Target : 1. Monitor progress on the implementation Vocational Internship Programme by 30 September 2024 | 386100 | 1. Progress Report | None | None
| 2 | Complete 1 Target: 1. Monitor progress on implementation Vocational Internship Programme by 30 December 2024 | 724680 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress on the implementation Vocational Internship Programme by 30 September 2024 2. Monitor progress on implementation Vocational Internship Programme by 30 December 2024 | 1110780 | 1. 2x Progress Reports | 2 Targets achieved,0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA: Vocational Internship Programme
Business Plan Reference | 3.7.1.5.13
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x vocational internship Programme for 24 unemployed learners implemented.
Budget Amount | R 1 000 000.00
Organisational Classification | Enterprise Development and support services / Services SETA: Vocational Internship Programme
Annual KPI | One (1) Vocational Internship programme implemented for 24 learners by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.13 | 1 | Complete 1 Target : 1. Monitor progress on the implementation Vocational Internship Programme by 30 September 2024 | 124740 | 1. Progress Report | None | None
| 2 | Completed 1 Target: 1. Monitor progress on implementation Vocational Internship Programme by 30 December 2024 | 249480 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress on the implementation Vocational Internship Programme by 30 September 2024 2. Monitor progress on implementation Vocational Internship Programme by 30 December 2024 | 374220 | 1. 2x Progress Reports | 2 Targets achieved, 0 Targets not achieved |  | 2
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA : Leanership Programme (Clothing Manufacturing Processes)
Business Plan Reference | 3.7.1.5.14
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 30 leaners
Budget Amount | R 168 850.43
Organisational Classification | Enterprise Development and support services / Services SETA : Leanership Programme (Sewing)
Annual KPI | Number of certificates issued leaners in 1x Learnership programmes by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5.14 | 1 | Complete 1 Target : Monitor progress on implementation of 1 learnership programme for 30 learners on Sewing by 30 September 2024 | 27720 | 1. Progress Report | None | None
| 2 | Completed 1 Target: Monitor progress on implementation of 1 learnership programme for 30 learners on Sewing by 30 December 2024 | 0 | 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Monitor progress on implementation of 1 learnership programme for 30 learners on Sewing by 30 September 2024 2. Monitor progress on implementation of 1 learnership programme for 30 learners on Sewing by 30 December 2024 | 27720 | 1. 2x Progress Reports | 2 Targets achieved, 0 Target not achieved |  | 2
[6 empty] | Total | 38 | 3

## TRADE & INVESTMENT PROMOTION
[7 empty] | Number of targets | Not achieved
Department | TRADE & INVESTMENT PROMOTION
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Economic Growth and Development
Business Plan Goal | 1. Sustainable inclusive economic growth 2.Economic infrastructure development
Business Plan Project | Cannabis and Hemp production
Business Plan Reference | 3.7.2.1
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | Draft District Cannabis Master Plan Developed
Annual Output | One Master Plan conducted by 30 June 2025
Budget Amount | R1500 000.00
Organisational Classification | Agriculture, Agro-processing and Forestry/Cannabis and Hemp production
Annual KPI | One Master Plan study conducted by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.2.1 | 1 | Complete 1 Target: Facilitate the advertisement of 1x service provider to conduct 1x Master Plan study by 30 September 2024 | R0.00 | Submit POE: 1. Terms of Reference 2. Advert | The project was discontinued due to financial constraints | The Agency is exploring the possibilities of collaboration with other entities to undertake this study
| 2 | Complete 1 Target: 1. Facilitate Advertisment of service provider to conduct 1x Master Plan study by 30 September 2024 2. Facilitate appointment of service provider to conduct 1x Master Plan study by 31 December 2024 2. Monitor the development of 1x Master Plan study by 31 December 2024 | R0.00 | Submit POE: 1. Appointment letter 2. Progress Report | The project was discontinued due to financial constraints | The Agency will be working with the ECRDA for the development of Cannabis and Hemp Master plan
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | The Advertisement of 1 x District Cannabis and Hemp Master Plan was not facilitated by 30 September 2024 2. Appointment of service provider to conduct 1x Master Plan study was not facilitated by 31 December 2024 3.Development of 1 x Master Plan study was not monitored by December 2024 | R0.00 | None | 0 Targets Achieved. 2 Target not Achived |  | 2 | 2
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Macadamia Nuts Plantation
Business Plan Reference | 3.7.2.2
Strategic Objective | To be recognised as a food basket for the region and markets beyond
Baseline | Pre-feasibility study
Annual Output | Feasibility study report
Budget Amount | R500,000.00
Organisational Classification | Agriculture, Agro-processing and Forestry/Macadamia Nuts Plantation
Annual KPI | One (1) bankable business plan on Macadamia Nuts plantation developed by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.2.2 | 1 | Complete 1 Target: 1. Recruitment of Service Provider to develop 1x bankable business plan by 30 September 2024 |  | Submit POE: 1. Advert 2. Terms of reference | The entity could not proceed with the Business Plan due to insufficient hectarage identified by the feasibility study | The Entity will invetigate more land to be feasibkle for the development of macadamia nuts plantations
| 2 | Complete 1 Target: 1.Undertake Appointment of service provider for development of 1x Bankable Business Plan for Macadamia Nuts Plantation . 2. Monitoring the progress on the development of bankable business plan by 31 December 2024 | R0.00 | Submit POE: 1.Appointment letter 2. Progress Report | The entity could not proceed with the Business Plan due to insufficient hectarage identified by the feasibility study | Targets will be adjusted in the mid -year
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1. Service Provider to develop 1x bankable business plan was not recruited by 30 September 2024. 2.Appointment of service provider for development of 1x Bankable Business Plan for Macadamia Nuts Plantation was not undertaken. 3. Progress on the development of bankable business plan was not monitored by 31 December 2024 | R0.00 | NONE | 0 Targets Achieved. 3 Target Not Achived |  | 2 | 2
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Agri Voltaic – SunFarming
Business Plan Reference | 3.7.2.3
Strategic Objective | To be recognised as a food basket for the region and markets beyond
Baseline | 0
Annual Output | 1x Feasibility study undertaken for Sunfarming in Alfred Nzo District
Budget Amount | R0.00
Organisational Classification | Agriculture, Agro-processing and Forestry / Agri Voltaic – SunFarming
Annual KPI | Secure 5 land parcels for for Sunfarming in Alfred Nzo District by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.2.3 | 1 | Compete 1 Target: 1.Facilitate availability of 1 land parcel for the implementation of Agri Voltaic- sunfarming project by 30 Septermber 2024 | R0.00 | Submit POE: 1. Progress Report | NONE | NONE
| 2 | Complete 1 Target : 1.Facilitate availability of 1 land parcels for the implementation of Agri Voltaic- sunfarming project by 30 September 2024 2. Facilitate availability of 1 land parcels for the implementation of Agri Voltaic- sunfarming project by 31 December 2024 | R0.00 | Submit POE: 1. Progress Report | NONE | NONE
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Availability of 1 land parcel for the implementation of Agri Voltaic- sunfarming project was facilitated by 30 Septermber 2024 | R0.00 | Progress Report | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Alfred Nzo Industrial Park
Business Plan Reference | 3.7.2.4
Strategic Objective | Mobilise resources for strategic economic infrastucture initiatives through the establishment of strategic partnerships.
Baseline | Pre- Feasibility undertaken
Annual Output | 1x Draft Feasibility study conducted on establishment of industrial Park by June 2025
Budget Amount | 500000
Organisational Classification | Local Economic Development / Alfred Nzo Industrial Park
Annual KPI | 1x Draft Feasibility study undertaken on establishment of industrial Park by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.2.4 | 1 | Compete 1 Target: 1. Stakeholder engagement to secure buy in from strategic partners by 30 September 2024 | R0.00 | Submit POE: 1. Stakeholder Report | None | None
| 2 | Complete 1 Target : 1. Mobilise co-funding to conduct feasibility study by 31 December 2024 | R0.00 | Submit POE: 1. Funding mobilisation Report | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Stakeholder engagement has been facilitated to secure buy in from strategic partners by 30 September 2024 2 .Co-funding to conduct feasibility study was mobilised by 31 December 2024. | R0.00 | 1. Stakeholder Report 2.Funding Mobilisation Report | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Resource Mobilisation
Business Plan Reference | 3.7.2.5
Strategic Objective | Mobilise resources for strategic economic infrastucture initiatives through the establishment of strategic partnerships.
Baseline | Resource Mobilisation Panel
Annual Output | R10 Million secured from 3rd funding
Budget Amount | R0.00
Organisational Classification | Enterprise Development and support services / Resource Mobilisation
Annual KPI | Amount of funding secured from 3rd Parties by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.2.5 | 1 | Compete 1 Target: 1.Stakeholder engagement to secure buy in from strategic partners by 30 Septermber 2024 | R0.00 | Submit POE: 1. Funding Proposal | None | None
| 2 | Complete 1 Target : 1. Develop and submit 1 funding proposal by 31 December 2024 | R0.00 | Submit POE: 1. Funding Proposal | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Stakeholder engagement has been facilitated to secure buy in from strategic partners by 30 Septermber 2024 2. 1x Funding proposal has been developed and submitted (WRSETA) by 30 Septermber 2024 | R0.00 | Funding Proposal | 2 Targets Achieved. 0 Target Not Achived |  | 2
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Partnerships
Business Plan Reference | 3.7.2.6
Strategic Objective | Mobilise resources for strategic economic infrastucture initiatives through the establishment of strategic partnerships.
Baseline | Signed MoUs
Annual Output | 2x strategic partners secured by June 2025
Budget Amount | R0.00
Organisational Classification | Enterprise Development and support services / Partnerships
Annual KPI | Number of partnership secured by 30 June 2025
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.2.6 | 1 | Compete 1 Target: 1. Facilitate development of stakeholder and partnership matrix by 30 September 2024 | R0.00 | Submit POE: 1. Partnership and stakeholder matrix | None | None
| 2 | Complete 1 Target : 1. Facilitate partnership with 1x strategic partner by December 2024 | R0.00 | Submit POE: 1. MoU/MOA | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Development of stakeholder and partnership matrix has been facilitated by 30 September 2024 2. Partnership with 1x strategic partner was facilitated by December 2024 | R0.00 | Partnership and stakeholder matrix MoU/MOA | 2 Targets Achieved. 0 Target Not Achived |  | 2
[6 empty] | Total | 12 | 4