## STRATEGIC ALIGNMENT
2. ANDA Alignment Criteria
2.1. Vision
“Leading a rapidly growing economy that generates wealth for its people”
2.2 Mission
To facilitate inclusive and innovative socio-economic growth through promoting sustainable enterprises development and implementation of high impact initiatives
2.3 Core Values
Ø Innovation;
Ø Accountability;
Ø Honesty;
Ø Fairness;
Ø Efficiency and effectiveness
The projects in the SDBIP have been crafted such that they are aligned to, and can contribute to the long-term and medium-term strategic planning documents of the District municipality as well as that of the Agency, namely the District Development Plan 2030, ANDM Integrated Strategic Plan (IDP) and Multi Year Business Plan.
DDP | IDP | ANDA
Goal 1: | Goal 2: | Goal 2:
An enabling infrastructure network | Basic Services Delivery and Community Empowerment | Economic Infrastructure Development
Goal 2: | Goal 4: | Goal 4:
Capable Democratic Governance | A capable and Financially viable institution | Good Governance
Goal 3
Effective Public Participation ,Good Governance and Partnerships
Goal 3: | Goal 1: | Goal 1:
An innovative, inclusive and growing economy | Inclusive Growth and Development | Sustainable Inclusive Economic Growth
Goal 3:
Sound Financial Management
Goal 4: | Goal 3: | Goal 4:
Environmental sustainability | Effective Public Participation, Good Governance and Partnerships | Good Governance
Goal 1
Sustainable Inclusive Economic Growth
Goal 5: | Goal 1: | Goal 1:
Rural Development and Innovative and high value agriculture | Inclusive Growth and Development | Sustainable Inclusive Economic Growth
Goal 6: | Goal 4: | Goal 5:
Improved Human Development | A Capable and financial viable institution | Enhancing Human Capabilities

## OVERALL PERFORMANCE
ALFRED NZO DEVELOPMENT AGENCY
ACHIEVED TARGETS VS NOT ACHIEVED BY DEPARTMENT
Unit | Total No. of targets | Achieved | Not Achieved | Achieved% | % Not Achieved
[8 empty] | 2024-2025 | 2025-2026
Programmes | 16 | 14 | 2 | 87.5% | 12.5% |  | Programmes | 95% | 87.5%
Trade & Investment Promotion | 6 | 5 | 1 | 83.33% | 16.67% |  | Trade & Investment Promotion | 67% | 83.33%
Finance and Admin | 17 | 16 | 1 | 94.12% | 5.882% |  | Finance and Admin | 94% | 94.12%
Office of the Chief Executive Officer | 6 | 4 | 2 | 66.67% | 33.33% |  | Office of the Chief Executive Officer | 58% | 66.67%
TOTAL | 45 | 39 | 6 | 86.67% | 13.33%
Department | 2024/2025 Mid-term Performance |  |  | 2025/2026 Mid-term Performance |  |  | Improved, Maintained or Declined
| Total No. of Targets | % Achieved | % Not Achieved | Total No. of targets | % Achieved | % Not Achieved | Outcome
Chief Executive Officer | 12 | 58% | 42% | 12 | 66.67% | 33.33% | Improved
Programmes | 38 | 95% | 5% | 16 | 87.5% | 12.5% | Declined
Trade and Investment | 12 | 67% | 33% | 6 | 83.33% | 16.67% | Improved
Finance and Administration | 49 | 94% | 6% | 17 | 94.12% | 5.882% | Improved
Overall Percentage | 111 | 87% | 13% | 51 | 86.67% | 13.33% | Improved

## FINANCE & ADMIN
3.7.3 FINANCE AND ADMINISTRATION | [6 empty] | Number of targets | Number of targets | Achieved | Not Achieved
Section Name | Supply Chain Management
National KPA
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Ensure timely, compliant, and cost-effective procurement processes that support uninterrupted service delivery
Business Plan Project | Procurement
Business Plan Reference | 3.7.3.1
Strategic Objective | Improve procurement efficiency and compliance to ensure timely and cost-effective delivery of goods and services
Baseline | Annual Implementation of SCM policy Reports produced
Annual Output | Timely processing and finalization of procurement transactions as per procurement plan and SCM turnaround times, with quarterly reports submitted reflecting compliance.
Budget Amount | 0
Organisational Classification | Supply Chain Management/Procurement Projects
Annual KPI | Number of annual procurement plans and quarterly procurement compliance reports submitted by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.1 | 1 | Complete 1 Target: 1. Develop one (1) annual procurement plan by 30 September 2025. 2. Produce one (1) Quarter 4 Supply Chain Management Report by 30 September 2025 | 0 | POE: 1. Approved Annual Procurment Plan 2. Quarterly Supply Chain Management Report by 30 September 2025. | N/A | N/A
| 2 | Complete 1 Target: 1. Produce one (1) Quarter 1 Supply Chain Management Report by 30 December 2025 | 0 | POE: 1.Quarterly Supply Chain Management Report by 31 December 2025.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. One annual procurement plan plan developed. Quarter 4 and Quarter 1 Supply Chain Management Reports produced. | 0 | POE: 1. Approved Annual Procurment Plan 2. Quarter 4 Supply Chain Management Report . 3. Quarter 1 Supply Chain Management Report . | 1 Target Achieved, 0 Targets not Achieved |  | 2 | 1 | 1 | 0
Section Name | Supply Chain Management
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Ensure proper safeguarding, monitoring, and verification of municipal assets to prevent loss and misstatement.
Business Plan Project | Asset Management
Business Plan Reference | 3.7.3.2
Strategic Objective | Ensure effective management, safeguarding and accurate reporting of municipal assets to promote service delivery, financial sustainability and audit readiness
Baseline | Financial Viability and financial Management
Annual Output | Verified and updated asset register supported by quarterly asset management reports (including fixed asset register updates, additions, verifications, and insured assets updates)
Budget Amount | 0
Organisational Classification | Asset Management
Annual KPI | Percentage of municipal assets physically verified annually by 30 June 2026. Number of asset-related audit findings by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.2 | 1 | Complete 1 Target: 1. To produce Quarter 1 Asset Management Report by 30 September 2025 dealing with: (3 x fixed asset registers (consolidated assets report), 3 x purchase listing report (additions), 1 x fixed asset verification report, 3 x monthly updates to the portfolio of assets insured) 2. 0% audit findings on assets | 0 | POE : 1.Quarterly Asset Management Report by 30 September 2025. | N/A | N/A
| 2 | Complete 1 Target: 1. To produce Quarter 2 Asset Management Report by 31 December 2025 dealing with: (3 x fixed asset registers (consolidated assets report), 3 x purchase listing report (additions), 1 x fixed asset verification report, 3 x monthly updates to the portfolio of assets insured) 2. 0% internal audit findings | 0 | POE : 1.Quarterly Asset Management Report by 31 December 2025
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Produced Quarter 1 and 2 Asset Management Reports by 31 December 2025 dealing with: (6 x fixed asset registers (consolidated assets report), 6 x purchase listing report (additions), 2 x fixed asset verification report, 6 x monthly updates to the portfolio of assets insured) 2. 0% audit findings on assets | 0 | POE: 1.Quarterly Asset Management Report by 30 September 2025. 2.Quarterly Asset Management Report by 31 December 2025 | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
Section Name | Supply Chain Management
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound Financial Management
Business Plan Project | Fleet Management
Business Plan Reference | 3.7.3.3
Strategic Objective | Safeguarding and maintenance of fleet
Baseline | 12 Fleet Management reports produced
Annual Output | Four (4)Fleet management reports produced by 30 June 2026
Budget Amount | 0
Organisational Classification | Supply Chain Management /Fleet Management
Annual KPI | Number of Fleet management reports produced by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.3 | 1 | Complete 1 Target: 1. To produce Quarter 1 Fleet Management Report by 30 September 2025 dealing with: (3 x fixed asset registers (consolidated assets report), 3 x purchase listing report (additions), 1 x fixed asset verification report, 3 x monthly updates to the portfolio of assets insured) | 0 | POE : 1.Quarterly Asset Management Report by 30 September 2025. | N/A | N/A
| 2 | Complete 1 Target: 1. To produce Quarter 2 Asset Management Report by 31 December 2025 dealing with: (3 x fixed asset registers (consolidated assets report), 3 x purchase listing report (additions), 1 x fixed asset verification report, 3 x monthly updates to the portfolio of assets insured) | 0 | POE : 1.Quarterly Asset Management Report by 30 December 2025.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Produced Quarter 1 and Quarter 2 Fleet Management Report by 31 December 2025 dealing with: (6 x fixed asset registers (consolidated assets report), 6 x purchase listing report (additions), 2 x fixed asset verification report, 6 x monthly updates to the portfolio of assets insured) | 0 | POE: 1. Quarterly Asset Management Report by 30 September 2025. 2. Quarterly Asset Management Report by 30 December 2025. | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Ensure accurate and timely preparation of mSCOA-aligned in-year reports in compliance with MFMA and National Treasury regulations
Business Plan Project | Budget & Reporting
Business Plan Reference | 3.7.3.4
Strategic Objective | Prepare accurate and reliable in-year reports, implement mSCOA budgeting and reporting.
Baseline | All compliance reports produced and submitted
Annual Output | Twenty (20) compliance report consisting of ( 1 x ANDA set of AFS,12 x Sec 87 reports (budget vs actual expenditure), 1 x Sec 88 Mid-term report, 4 x Quarterly in-year Financial and performance Reports), ANDA 2026/27 Final Budget, ANDA 2025/26 Adjusted Budget) submitted by 30 June 2026
Budget Amount | 401120
Organizational Classification | Finance/ Budget & Reporting
Annual KPI | Number of compliance reports produced and submitted by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.4 | 1 | Complete 1 Targets: 1. To facilitate submission of 2024/25 AFS to AG 2. To Prepare and submit ANDA compliance reports to the office of the CEO by 30 September 2025 entailing ( 3 x Section 87 Reports, Quarter 4 In year Financial and perfomance Report | 233570.13 | POE: 1. GRAP Compliant 2023/24 AFS and proof of submission to AG 2. Compliance Reports 3. Proof of submission | N/A | N/A
| 2 | Complete 1 Targets: 1. To facilitate submission of Adjusted AFS to AG by 31 December 2025 2. To Prepare and submit ANDA compliance reports to the office of the CEO by 31 December 2025 entailing ( 3 x Section 87 Reports, Quarter 1 In year Financial and perfomance Report) 3. To recieve a Draft & final Audit report. | 0 | POE: 1. Adjusted AFS and proof of submission to AG 2. Compliance Reports 3. Proof of submission 4. Draft & final Audit report.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Annual Financial Statements submitted to the AG by 31 December 2025 2.Facilitated submission of Adjusted AFS to AG by 31 December 2025 3. Prepared and submitted ANDA compliance reports to the office of the CEO by 31 December 2025 entailing ( 6 x Section 87 Reports, Quarter 1 In year Financial and perfomance Report) 4. Received a Draft & final Audit report. | 0 | POE: 1. GRAP Compliant 2024/25 AFS and proof of submission to AG 2. Compliance Reports 3. Proof of submission 4. Adjusted AFS and proof of submission to AG 5. Compliance Reports 6. Proof of submission 7. Draft & final Audit report. | 1 Target Achieved, 0 Target not Achieved |  | 5 | 1 | 1 | 0
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Sound financial management
Business Plan Project | Financial Information Systems
Business Plan Reference | 3.7.3.5
Strategic Objective | Comply with National Treasury mSCOA regulations
Baseline | mSCOA implementation Plan,(mSCOA Progress Reports), Proof of payment of service fees
Annual Output | Monitoring implementation of one (1) mSCOA Financial Accounting System.
Budget Amount | R 1 346 691,65
Organizational Classification | Finance/Financial Information Systems
Annual KPI | Number of system reports generated by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.5 | 1 | Complete 1 Target: 1. To produce one (1) quartely System Report (GL and TB) by 30 September 2025. | R336 672.91 | POE: 1. System Report | N/A | N/A
| 2 | Complete 1 Target: 1.To produce one (1) quartely System Report (GL and TB) by 31 December 2025. | R336 672.91 | POE: 1. System Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Produced two (2) quartely System Report (GL and TB) by 31 December 2025. | 518091.28 | POE: 1.Systems Report (General ledger and Trial Balance | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | A Capable and Financially Viable Institution
Business Plan Goal | Achieve a clean audit opinion through effective financial management and compliance
Business Plan Project | Improved audit opinion
Business Plan Reference | 3.7.3.6
Strategic Objective | Attain and sustain clean audit outcomes through sound financial governance, strengthened internal controls, and proactive risk management.
Baseline | Unqualified audit opinion with no findings
Annual Output | Audit report with no material findings
Budget Amount | R 1 338 000,00
Organizational Classification | Finance/Revenue & Expenditure
Annual KPI | Number of Unqualified audit reports with no findings by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.6 | 1 | Complete 1 Target: 1. To produce 3X deliverable entailing of Investment Reconciliations, 3x PAYE Reconciliationst , 2x VAT reconciliation, 3x Bank Reconciliation Report, 3x Creditors Reconciliation by 30 September 2025. | 334500 | POE: 1. 1 x Compliance Report | The quartely budget was estimated based on previous years quarterly expenditure without including the payment of licence fees in the first quarter. | None, Because annual budget has not been exceeded. The over expenditure will be cancelled by a positive annual budget that has not been exceeded.
| 2 | Complete 1 Target: 1. To produce 3X deliverable entailing of Investment Reconciliations, 3x PAYE Reconciliationst , 2x VAT reconciliation, 3x Bank Reconciliation Report, 3x Creditors Reconciliation by 31 December 2025. | 334500 | POE: 1. 1 x Compliance Report 2. Audit report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Produced 6X deliverable entailing of Investment Reconciliations, 6x PAYE Reconciliationst , 4x VAT reconciliation, 6x Bank Reconciliation Report, 6x Creditors Reconciliation by 31 December 2025. | 952728.7 | POE: 1.Compliance reports (Reconciliations), and Audit Report | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
Department
Department | Supply Chain Management
Section Name | Finance
National KPA | Financial Viability and Financial Management
IDP Goal (s) | Sound financial management
Business Plan Goal | Reduce irregular expenditure through improved supply chain compliance, internal controls, and proactive risk management.
Business Plan Project | Elimination Irregular Expenditure Project
Business Plan Reference | 3.7.3.7
Strategic Objective | Prevent and reduce irregular, fruitless and wasteful expenditure through strengthened internal controls, effective supply chain management practices, and full compliance with applicable legislation
Baseline | R5 848 042 fruitless and wasteful expenditure ; R9 609 691 irregular expenditure.
Annual Output | Four (4) ANDA Irregular Expenditure reports
Budget Amount | R0.00
Organisational Classification | Finance/Irregular Expenditure
Annual KPI | Percentage reduction in irregular, fruitless and wasteful expenditure compared to prior year by 30 June 2026.
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.3.7 | 1 | Complete 1 Targets: 1. 75% reduction by 30 September 2025. | R 0.00 | POE: 1. 100% reduction by 31 December 2025. | N/A | N/A
| 2 | Complete 1 Targets: 1. 100% reduction by 31 December 2025. | R 0.00 | POE: 1.Irregular Expenditure report | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.100% reduction on irregular expenditure by 31 December 2025 | 0 | POE: 1. Irregular Expenditure Report 2. Fruitless and Wasteful Expenditure Report | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
e
Section Name | Huma Resource Management
National KPA | Municipal Transformation and Organisational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Policy Development
Business Plan Reference | 3.7.3.8
Strategic Objective | Ensure compliant controlled environment
Baseline | Entity approved 2024/2025 Policies
Annual Output | 54 ANDA 2025/2026 Policies developed, reviewed and Submitted to the office of the CEO by 30 June 2026
Budget Amount | 0
Organisational Classification | Human Resource Management/Policy Development
Annual KPI | Number of Entity policies reviewed and submitted to the Office of the CEO by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for variance | Corrective Measures
7.3.8 | 1 | Complete 1 Target: 1. Monitor implementation of ANDA Policies by 30 September 2025 | R0.00 | POE: 1. Monitoring Report | N/A | N/A
| 2 | Complete 1 Target: 1. Monitor implementation of ANDA Policies by 31 December 2025 2. Circulate the Policy Review Template to all Departments by 31 December 2025 | 0 | POE: 1. Monitoring Report | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Implementation on ANDA Policies has been monitored by 30 September and 31 December 2025 2. Policy Review Template has been circulated to all departments by 31 December 2025 | 0 | POE: 1.Quarter 1 and 2 Monitoring reports | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
Section Name | Human Resource Management
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Project | Payroll Management
Business Plan Reference | 3.7.3.9
Strategic Objective | Ensure efficient and effective payroll system, compliant with legislative requirements
Baseline | 12 payroll runs processed; tax returns submitted as required
Annual Output | Payroll runs processed and tax returns submitted in compliance with legislative requirements
Budget Amount | R 13 396 420.43
Organisational Classification | Human Resource Management /VIP Payroll
Annual KPI | Number of payroll run reports prepared and approved by the CEO and 1x bi-annual Tax return and 1x annual Tax returns submitted to SARS by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for variance | Corrective Measures
7.3.9 | 1 | Complete 1 Target: 1.To process 3 payroll runs by 30 September 2025 2. Submit bi-annual Tax return to SARS by 30 September 2025 | R 3 349 105.11 | POE: 1.Payrol Report, EMP201 Report 2. Proof of bi-annual tax return submission | N/A | N/A
| 2 | Complete 1 Target: 1. To process 3 payroll runs by 31 December 2025 | R 3 349 105.11 | POE: 1. 3 Payrol Report, EMP501 Report.
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Processed 6 payroll runs by 31 December 2025 and submitted bi-annual Tax return to SARS by 30 September 2025 | 4761175 | POE: 1. Six Payrol Reports , 2. Six (6) EMP201 Reports 3. Proof of bi-annual tax return submission 4. One (1) EMP501 Report. | 1 Target Achieved, 0 Target not Achieved |  | 3 | 1 | 1 | 0
Section Name | Human Resource Management
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Staff Establishment Review
Business Plan Reference | 3.7.3.10
Strategic Objective | Ensure Appropriate Organisational Structure to deliver on the Vision of the Strategy
Baseline | 1 x Reviewed and adopted 2024/2025 staff establishment
Annual Output | Reviewed and approved 2025/2026 Staff establishment
Budget Amount | 0
Organisational Classification | Human Resource Management/Organogram Review
Annual KPI | Number of staff staff establishment reviewed and approved by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for variance | Corrective Measures
7.3.10 | 1 | Complete 1 Targets: 1.Monitor Implementation of 2025/2026 Staff Establishment by 30 September 2025 | R 0.00 | POE: 1. Report on vacancies filled as per the approved staff establishment | N/A | N/A
| 2 | Complete 1 Targets: 1.Monitor Implementation of 2024/2025 Staff Establishment by 30 December 2025 | R 0.00 | POE: 1.Report on vacancies filled as per the approved staff establishement | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Monitor Implementation of 2025/2026 Staff Establishment by 30 September 2025 and 31 December 2025 | 0 | POE: 1. Quarter 1 and 2 reports on vacancies filled as per the approved staff establishment | 1 Target Achieved, 0 Target not Achieved |  | 2 | 1 | 1 | 0
Section Name | Human Resource Development
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Skills Development
Business Plan Reference | 3.7.3.11
Strategic Objective | To promote the development of Human Resource Capacity
Baseline | Training and Skills Development Policy
Annual Output | One (1) approved Annual Training Plan 2025/26, training report for trainings conducted and Workplace Skills Plan (WSP) submitted by 30 June 2026
Budget Amount | 150000
Organisational Classification | Human Resource Development/Skills Development
Annual KPI | Number of training plans approved. Number of staff consultation conducted. Number of WSPs submitted to LGSETA and number of SDF meetings attended by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly Means of Verifications | Reasons for variance | Corrective Measures
7.3.11 | 1 | Complete 1 Target: 1. Facilitate training as per WSP and ATP by 30 September 2025 2. Attend Quarterly SDF Meeting (Skills Development Forum) by 30 September 2025 | R 50 000.00 | POE: 1. Registers for trainings conducted 2. Attendance Register for SDF Meetings | N/A | N/A
| 2 | Complete 1 Target: 1. Conduct one (1) Skills Audit for all employees 2. Develop Draft Annual Training Plan 3. Attend Quarterly SDF Meeting (Skills Development Forum) by 31 December 2025 | R 50 000.00 | POE: 1. Skills Audit Forms 2. Draft Annual Training Plan 3. Attendance Register for consultation 4. Attendance Register for SDF Meetings | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Facilitated training as per WSP and 1, ATP by 30 September 2025; 2. Attended Quarterly SDF Meeting (Skills Development Forum) by 30 September 2025; 3. Conducted one (1) Skills Audit for all employees; 4. Developed a Draft Annual Training Plan; 5. Attended Quarterly SDF Meeting (Skills Development Forum) by 31 December 2025. | 0 | POE: 1. Registers for trainings conducted 2. Attendance Register for SDF Meetings 3. Skills Audit Forms 4. Draft Annual Training Plan 5. Attendance Register for consultation 6. Attendance Register for SDF Meetings | 1 Target Achieved, 0 Target not Achieved
[7 empty] | 5 | 1 | 1 | 0
Section Name | ICT
National KPA | Municipal Transformation and Organizational development
IDP Goal (s) | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | ICT Management
Business Plan Reference | 3.7.3.12
Strategic Objective | Effective Communication and Information Management
Baseline | No ICT strategy
Annual Output | Approved ICT Governance Strategy, Policy, and Implementation Plan Strategy
Budget Amount | R0.00
Annual KPI | Number of ICT strategies reviewd and developed by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amounts ( Quarter) | Quarterly Means Of Verifications | Reasons for variance | Corrective Measures
7.3.12 | 1 | Complete 1 Target: 1. Conduct one situational analysis and stakeholder needs assessment by 30 September 2025 | R 0.00 | POE: 1. Assessment Report | N/A | N/A
| 2 | Complete 1 Target: 1. Drafting of one Strategy and Plan by 31 December 2025 | R 0.00 | POE: 1. Draft ICT governance strategy, policy and plan | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1Target: 1. Conducted one situational analysis and stakeholder needs assessment by 30 September 2025 and drafted one Strategy and Plan by 31 December 2025 | 0 | POE: 1. Assessmwent Report 2. Draft ICT governance strategy, policy and plan | 1 Target Achieved, 0 Target not Achieved
[7 empty] | 1 | 1 | 1 | 0
Section Name | Administration
National KPA | Municipal Transformation and Organisational Development
IDP Goal | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Records Management
Business Plan Reference | 3.7.3.13
Strategic Objective | To safeguard Organisational memory and Archives
Baseline | 1 manual general filing system developed and implemented
Annual Output | One (1) report on the implementation of Manual general filling system, Establishment and Monitoring of Archives by June 2026
Budget Amount | R0.00
Organisational Classification | Administration/Records Management
Annual KPI | Number of monitoring reports for implementation of one (1) approved manual general filling system and Establishment of Secure Archives by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amounts ( Quarter) | Quarterly Means Of Verifications | Reasons for Variance | Corrective Measures
7.3.13 | 1 | Complete 1 Target: 1.Monitor one General Filing System by 30 September 2025 2. Establish secured Archives section by 30 September 2025 | R 0.00 | POE: 1. Draft Manual General filling system 2. Orders for procurement of cabinets | N/A | N/A
| 2 | Complete 1 Target: 1. Monitor one General Filing System by 31 December 2025 | R 0.00 | POE: 1.Attendance Register for the workshop | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. General Filing System was monitored by 30 September 2025 and 31 December 2025 | 0 | POE: 1. Draft Manual General filling system 2. Orders for procurement of cabinets 3. Attendance Register for the workshop | 1 Target Achieved, 0 Target not Achieved
[7 empty] | 3 | 1 | 1 | 0
Section Name | Individual and Institutional Performance Management
National KPA | Municipal Transformation and Organizational development
IDP Goal | A capable and financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Individual Performance Management
Business Plan Reference | 3.7.3.14
Strategic Objective | Improve performance and efficiency level
Baseline | PMS Policy Framework is in place and PMS Workshop was conducted to all employees
Annual Output | 7 x Performance Agreements for Senior Managers and Middle developed and approved, divisional score cards, accountability agreements, performance promises by 30 June 2026
Budget Amount | R0.00
Municipal Classification | IPMS /Performance Management System
Annual KPI | 100% employees signed performance agreements and performance assessments conducted to all employees by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Quartely Budget | Quarterly Means of Verifications | Reasons for Varience | Corrective Measures
7.3.14 | 1 | Complete 1 Targets: 1. Draft and submit 7 individual Performance Agreements and submit to the Office of the CEO by 30 September 2025 2. Update all Individual PMS Templates ( divisional score cards, accountability agreements, performance promises) and submit to all HODs by 30 July 2025. 3. Coordinate submission of Annual Performance Plans by all ANDA Employees by 30 July 2025 | R 0.00 | POE: 1. 4x Signed performance agreements, 2. 3x divisional scorecards, 5x Accountability Agreements, 2x Performance promises 3. 14x Annual Performance Plans | The performance agreement of the CEO was not finalised, therefore executive manager's performance contracts could not be signed. | Finalise signing of performance agreements
| 2 | Complete 1 Targets: 1. Conduct one PMS Workshop to all Entity employees by 31 December 2025 2.Cordinates performance reviews for all employees and assesment for all entity employees by 31 December 2025 | 0 | POE: 1.Attendance Register for the PMS Workshop | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Draft and submit 7 individual Performance Agreements and submit to the Office of the CEO by 30 September 2025 2. Update all Individual PMS Templates ( divisional score cards, accountability agreements, performance promises) and submit to all HODs by 30 July 2025. 3. Coordinate submission of Annual Performance Plans by all ANDA Employees by 30 July 2025 4. Conduct one PMS Workshop to all Entity employees by 31 December 2025 2.Cordinates performance reviews for all employees and assesment for all entity employees by 31 December 2025 | 0 | POE: 1. 4x Signed performance agreements, 2. 3x divisional scorecards, 5x Accountability Agreements, 2x Performance promises 3. 14x Annual Performance Plans | 0 Target Achieved, 1 Target not Achieved |  | 5 | 1 | 0 | 1
Section Name | Auxilary Services
National KPA | Municipal Transformation and Organisational Development
IDP Goal | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Cleaning Goods and Services
Business Plan Reference | 3.7.3.15
Strategic Objective | Ensure hygiene and clean work environment
Baseline | Cleaning Services
Annual Output | Monitoring of Cleaning Services by 30 June 2026
Budget Amount/Budget | R 120 000.00
Organisational Classification | Auxilary Services/Cleaning Services
Annual KPI | Number of cleaning services monitored by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Quarterly Budget | Quarterly Means Of Verifications | Reasons for Varience | Corrective Measures
7.3.15 | 1 | Complete 1 Targets: 1. Submit one (1) monitoring report on the contracted cleaning service provider by 30 September 2025. | 30000 | POE: 1. Monitoring Register | N/A | N/A
| 2 | Complete 1 Targets: 1. Submit one (1) monitoring report on the contracted cleaning service provider by 31 December 2025 | 30000 | POE: 1. Monitoring Register | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Cleaning services has been monitored by 30 September and 31 December 2025 | 60000 | POE: 1. Quarter 1 and 2 monitoring register | 1 Target Achieved, 0 Target not Achieved
[7 empty] | 2 | 1 | 1 | 0
Section Name | Human Resource Management
National KPA | Municipal Transformation and Organizational development
IDP Goal | A capable and a financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Recruitment and Selection
Business Plan Reference | 3.7.3.16
Strategic Objective | Ensure capable workforce to deliver on the Vision of the Strategy
Baseline | 2024/2025 Approved Organisational structure
Annual Output | 6 Vacant positions filled as per 2025/2026 approved Staff Establishment
Budget Amount | R25 000.00
Organisational Classification | Human Resource Management/Recruitment and Selection
Annual KPI | Number of vacant positions filled as per approved Staff Establishment by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Quarterly Budget | Quarterly Means Of Verifications | Reasons for Varience | Corrective Measures
7.3.16 | 1 | Complete 1 target: 1. Develop and Coordinate approval of the Recruitment Plan and submit to the office of the CEO inline with the budgeted positions on the approved staff establishment by 30 September 2025 2. Coordinate appointment of the 2 Advertised positions (CEO and Manager: Budget, Expenditure and Reporting) | R 6 250.00 | POE: 1.Recruitment Plan | N/A | N/A
| 2 | Complete 1 target: 1. Facilitate advertising of 4 vacant positions as per the approved recruitment plan by 31 December 2025 | R 6 250.00 | POE: 1. Adverts for 3 positions | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Develop and Coordinate approval of the Recruitment Plan and submit to the office of the CEO inline with the budgeted positions on the approved staff establishment by 30 September 2025 2. Coordinate appointment of the advertised positions | 8857.69 | POE: 1. Recruitment Plan 2. Adverts for posts | 1 Target Achieved, 0 Target not Achieved |  | 3 | 1 | 1 | 0
Section Name | Human Resources Management
National KPA | Municipal Transformation and Organizational development
IDP Goal | A capable and financially viable institution
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Occupation Health and Safety
Business Plan Reference | 3.7.3.17
Strategic Objective | Ensure healthy and safety working Environment
Baseline | Approved OHS Policy
Annual Output | Conduct 4x OHS committee meetings, Submit 1 x OHS Action Plan, Submit 1x Assessment Compliance Reports in all respect with the OHSA and the COIDA and the regulations framed under the acts by 30 June 2026
Budget Amount | R100 000.00
Municipal Classification | OHS /Occupational Health and Safety
Annual KPI | Number of OHS committes appointed, Number of OHS meeting conducted by 30 June 2026
SDBIP Reference | Quarter | Quarterly Target | Quartely Budget | Quartelry Means of Verification | Reasons for Varience | Corrective Measures
7.3.17 | 1 | Complete 1 Targets: 1. Cooardinate Appointment of OHS Committee members by 30 July 2025 2. Submit 1x Annaul OHS Action Plan to the Office of the CEO for approval by 30 September 2025 3. Monitor the sitting of the Health and Safety committee meeting to ensure compliance to OHAS-Act by 30 September 2025 | R25 0000.00 | POE: 1. Appointment Letter for OHS Committee 2. Approved Annual OHS Action Plan 3. Minutes and Attendance register of the meeting | N/A | N/A
| 2 | Complete 1 Targets: 1. Monitor the sitting of the Health and Safety committee meeting to ensure compliance to OHAS-Act by 31 December 2025 2. Conduct 1x Assessment Compliance Report on ANDA Building 2. Coordinate Training of OHS Committee members by 31 December 2025 | R25 000.00 | POE: 1. Minutes and Attendance register for Health and Safety commitee meeting | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Appointment of OHS Committee by 30 September 2025. Quarter 1 and 2 meetings, development and apporval of Annual OHS Plan. | 0 | POE: 1. Appointment Letter for OHS Committee 2. Approved Annual OHS Action Plan 3. Minutes and Attendance register of the meeting Q1 4. Minutes and Attendance register for Health and Safety commitee meeting Q2 | 1 Target Achieved, 0 Target not Achieved |  | 6 | 1 | 1 | 0
[6 empty] | Total | 49 | 17 | 16 | 1

## OCEO
[7 empty] | Number of targets | Achieved | Not Achieved
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | 100% Good Governance Compliance
Business Plan Reference | 3.7.4.1
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Board meetings, Strategic Planning Session and Annual general meeting held
Annual Output | 4x compliance registers, 4x approved finanacial reports and 4x approved performance reports by 30 June 2026
Budget Amount | R 710 000.00
Organisational Classification | Corporate Governance, Legal Compliance and Services /Sitting of Board Meetings, Monitoring, Evaluation and Reporting
Annual KPI | Number of compliance registers, Number of approved quarterly finanacial reports, Number of approved performance reports by 30 June 2026.
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.4.1 | 1 | Complete 1 Target: 1. Develop compliance register 2. 100% Board Support | 177500 | POE: 1. Compliance register 2. Approved Quarterly financial reports 3. Approved quarterly performance reports | The varience is due to special board meetings which exceeded the planned meetings as a result of the newly appointed Board members and CEO who needed induction as part of their onbording. The Entity did not get clean audit opinion but rather obtained unquliefied audit from the Auditor General | To minimize the number of special board meetings. The Entity will work hard towards achieving clean audit opinion.
| 2 | Complete 1 Target: 1. Reviewed compliance register 2. 100% Board Support 3. Clean Audit Opinion | 177500 | POE: 1. Compliance register 2. Approved Quarterly financial reports 3. Approved quarterly performance reports 4. AG Management Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Quarterly means of Verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Targets: 1. Developed compliance register 2. Reviewed compliance register 3. 100% Board Support 4. Obtained Unqulified Audit | 443 492.47 | POE: 1. Compliance register 2. Approved Quarterly financial reports 3. Approved quarterly performance reports 4. AG Management Report | 0 Target achieved, 1 Targets not achieved |  | 1 | 0 | 1
Section Name | Communications
National KPA | Good governance and public participation
IDP Goal (s) | Effective Public Participation, Good Governance
Business Plan Goal | Good Governance
Business Plan Project | Communications project
Business Plan Reference | 3.7.4.2
Strategic Objective | Promotion of stakeholders realations and positive public image of ANDA
Baseline | Implementation of ANDA Communications and Marketing Strategy
Annual Output | 1x Workshop report, 1x final communication plan and 1x Survey road map by 30 June 2026.
Budget Amount | R0.00
Organisational Classification | Communications
Annual KPI | Number of Communications workshop held, number of communication plan develop and number of survey road map developed by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.4.2 | 1 | Complete 1 Target: 1. To hold Communications Workshop by 30 September 2025 | R 0.00 | POE: 1. Workshop Report | N/A | N/A
| 2 | Complete 1 Target: 1. To draft 2025/2026 Communications Plan | R 0.00 | POE: 1. Draft communications Plan 2025/2026
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Quarterly means of Verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Targets: 1. Held Communications Workshop by 30 September 20252 2. Drafted 2025/2026 Communications Plan. | R0.00 | POE: 1. Workshop Report 2.Draft communications Plan 2025/2026 | 1 Targets Achieve, 0 Tagets not achieved |  | 1 | 1 | 0
Section Name | Individual and Institutional Performance Management
National KPA | Good Governance and Public Participation
IDP Goal | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Enhancing Human Capabilities, Organisational efficiency and effectiveness
Business Plan Project | Institutional Performance Management
Business Plan Reference | 3.7.4.3
Strategic Objective | To strengthen institutional reporting, compliance and performance level
Baseline | All compliance reports produced and submitted
Annual Output | 4 Quarterly Performance and financial reports, 1x Annual Performance Report, 1x Midterm Performance Report , 1x Annual Report and 12x monthly management meetings submitted by 30 June 2026
Budget Amount | R 0,00
Organisational Classification | IIPM/Planning and Reporting
Annual KPI | Number of Quartely Performance and Financial reports, Number of Annual Performance Report, Number of Annual Report , Number of monthly management meetings and Number of Midterm Performance Report submitted to the Board by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.4.3 | 1 | Complete 1 Target: 1. Consolidate and Review Q1 in year Performance and Financial Report by 30 of September 2025 2. Consolidate and Review Annual Perfomance Report by 30 of September 2025. 3. Hold 3x Monthly Management Meeting by 30 September 2025 | R0.00 | POE: 1. Proof of submissions to APC, Board and ANDM | N/A | N/A
| 2 | Complete 1 Target: 1. Consolidate and Review Q2 in year Performance and Financial Report by 15 October 2025 2. Consolidate and Submit Annual Report by 15 December 2025 3.Hold 3x Monthly Management Meeting by 31 December 2025 | R0.00 | POE: 1. Proof of submissions to APC, Board and ANDM
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Quarterly means of Verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Consolidated and Reviewed Q1&Q2 in year Performance and Financial Report by 30 of December 2025 2. Consolidated and Reviewed Annual Perfomance Report by 30 of September 2025. 3. Held 6x Monthly Management Meeting by 30 December 2025 4. Consolidated and Submit Annual Report by 15 December 2025 | R0.00 | POE: 1. Proof of submissions to APC, Board and ANDM | 1 Targets Achieved, 0 Targets not achieved |  | 1 | 1 | 0
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Internal Audit
Business Plan Reference | 3.7.4.4
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Reviewed ANDA Internal Audit Reports
Annual Output | 1x reviewed IA Charter,1x reviewed APC Charter and 3x quarterly internal audit reports by 30 June 2026
Budget Amount | R0
Organisational Classification | Corporate Governance and Legal Compliance /Internal Audit
Annual KPI | Number of quartely reviews undertaken by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.4.4 | 1 | Complete 1 Target: 1. Review Internal Audit Charter by 30 June 2025 2. Revise Audit and Performance Committe Charter by 30 June 2025 | R0.00 | POE: 1. Reviewed IA Chater 2. Reviewed APC Charter | N/A | N/A
| 2 | Complete 1 Target: 1. 100% implementation of Internal Audit Plan by 30 December 2025 | R0.00 | POE: 1. Quarterly Internal Audit Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Quarterly means of Verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Reviewed Internal Audit Charter by 30 June 2025 2. Revised Audit and Performance Committe Charter by 30 June 2025 3. 100% implementation of Internal Audit Plan by 30 December 2025 | R0.00 | POE: 1. Reviewed IA Chater 2. Reviewed APC Charter 3.Quarterly Internal Audit Report | 1 Targets Achieved, 0 Targets not achieved |  | 1 | 1 | 0
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Risk Management
Business Plan Reference | 3.7.4.5
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Reviewed Risk Register
Annual Output | 1x Workshop, 1x Risk Management strategy and plan and 3x quarterly reviewed registers by 30 June 2026
Budget Amount | R0.00
Organisational Classification | Corporate Governance and Legal Compliance /Risk Management
Annual KPI | Number of quartely reviews undertaken , Number of Risk Management Strategy and Plan developed and Number Risk Management Workshops held by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.4.5 | 1 | Complete 1 Target: 1. Hold Risk Management Workshop by 30 September 2025 2. Draft Risk Management Strategy and Plan by 30 September 2025 | R0.00 | POE: 1. Workshop Report 2. Draft Risk Management Strategy and Plan | N/A | N/A
| 2 | Complete 1 Target: 1. Finalise Risk Management Strategy and Plan by 30 September 2025 2. Review Risk Register | R0.00 | POE: 1. Reviewed Risk Register 2. Finalized Risk Management Strategy and Plan
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Quarterly Means of Verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Held Risk Management Workshop by 30 September 2025 2. Drafted Risk Management Strategy and Plan by 30 September 2025 3. Finalised Risk Management Strategy and Plan by 30 September 2025 4. Reviewied Risk Register | R0.00 | POE: 1. Workshop Report 2. Draft Risk Management Strategy and Plan 3. Reviewed Risk Register 4. Finalized Risk Management Strategy and Plan | 1 Targets Achieved, 0 Targets not achieved |  | 1 | 1 | 0
Department | Office of the CEO
Section Name | Corporate Governance, Legal Compliance and Services
National KPA | Good Governance and Public Participation
IDP Goal (s) | Effective Public Participation, Good Governance and Partnerships
Business Plan Goal | Good Governance
Business Plan Project | Legal Services
Business Plan Reference | 3.7.4.6
Strategic Objective | To Strengthen Governance, Reduce Risk, Increase performance and efficiency within the Entity
Baseline | Reviewed Litigations Reports
Annual Output | 4x Quarterly ANDA litigations Reports by 30 June 2026
Budget Amount | R 150 000.00
Organisational Classification | Corporate Governance and Legal Compliance/Legal Services
Annual KPI | Number of quarterly reviews undertaken by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.4.6 | 1 | Complete 1 Target: 1. 80% Reduction of litigations by 30 September 2025 | R37 500.00 | POE: 1. Litigations Report | The variance is due to delays in obtaining court dates. The over spending rexpenditure was due to emerging litigation against ANDA which was not budgeted for. | The outstanding litigations will be heard by 30 June 2026. The Entity will make provision foir unforseen litigation.
| 2 | Complete 1 Target: 1. 80% Reduction of litigations by 31 December 2025 | R37 500.00 | POE: 1. Litigations Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. 80% Reduction of litigations by 31 December 2025 | 408765.02 | POE: 1. Litigations Report | 0 Targets Achieved, 1 Targets not achieved |  | 1 | 0 | 1
[6 empty] | Total | 6 | 4 | 2

## TRADE & INVESTMENT PROMOTION
[7 empty] | Number of targets | Achieved | Not Achieved
Department | TRADE & INVESTMENT PROMOTION
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Economic Growth and Development
Business Plan Goal | 1. Sustainable inclusive economic growth 2.Economic infrastructure development
Business Plan Project | Cannabis production
Business Plan Reference | 3.7.2.1
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | None
Annual Output | One Master Plan conducted by 30 June 2026
Budget Amount | 600000
Organisational Classification | Agriculture, Agro-processing and Forestry/Cannabis and Hemp production
Annual KPI | Number of Master Plans study developed by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.2.1 | 1 | Complete 1 Target: 1.Facilitate the appointment of Service Provider for the development of cannabis master plan by 30 September 2025 2. Hold Engagement with ECRDA by 30 September 2025 | R 50 000.00 | POE: 1. Appointment Letter 2. Engagegements Report | The appointment of the service provider could not be finalised due delays eminating from absence of responsive bidders in the first attempt of recruitment. the first Bid advert was closed on the 08 September 2025. | Readvert was issued in the 2nd quarter of the 2025/2026 financial year as part of sourcing responsive bidders. Appointment of responsive Bidders will be undertaken in the 3rd quarter
| 2 | Complete 1 Target: 1. Hold an inception meeting with the Service Provider by 31 December 2025 2. Monitor the development of Master Plan by 31 December 2025 | R 200 000.00 | POE: 1. Inception Report 2. Draft Master Plan Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Appointment of Service Provider for the development of district cannabis master plan was facilitated but not finalised by 30 September 2025, 2. Engagement with ECRDA was held in East London on 11 August 2025. | R 0.00 | N/A | 0 Target achived, 1 Target not achieved |  | 1 | 0 | 1
Department | TRADE & INVESTMENT PROMOTION
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Macadamia Nuts Plantation
Business Plan Reference | 3.7.2.2
Strategic Objective | To be recognised as a food basket for the region and markets beyond
Baseline | Pre-feasibility study
Annual Output | Feasibility study report by 30 June 2026
Budget Amount | R300 000.00
Organisational Classification | Agriculture, Agro-processing and Forestry/Macadamia Nuts Plantation
Annual KPI | Number of social facilitation engagements conducted by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.2.2 | 1 | Complete 1 Target: 1.Faciliate the appointment of social facilitator by 30 September 2025 | R20 000.00 | POE: 1.Appointment letter | The under-expenditure is due to the non-payment of the service provider following delays in the completion of certain activities that were scheduled for the second quarter. The entity only makes payments for activities that have been verified in accordance with the SLA. | The funds will be paid in Quarter 3 once all necessary activities have been completed in accordance with the SLA.
| 2 | Complete 1 Target: 1. Monitoring the undertaking of social facilitation by 31 December 2025 | R100 000.00 | POE: 2.Inception Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Appointment of social facilitator was facilitated by 30 September 2025. The Bid advert closed on the 08 September 2025 2. The undertaking of social facilitation was monitored by the 31 December 2025 | R0.00 | POE: 1.Appointment letter 2. Inception Report | 1 Target achived, 0 Targets not achieved |  | 1 | 1 | 0
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Agri Voltaic – SunFarming
Business Plan Reference | 3.7.2.3
Strategic Objective | To be recognised as a food basket for the region and markets beyond
Baseline | 0
Annual Output | Approved Lease agreement secured by 30 June 2026
Budget Amount | R400 000.00
Organisational Classification | Agriculture, Agro-processing and Forestry / Agri Voltaic – SunFarming
Annual KPI | Number of land surveys conducted at Tholeni Administrative Area by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly means of Verification | Reasons for Variance | Corrective Measures
7.2.3 | 1 | Compete 1 Target: 1.Faciliate the appointment of service provider to conduct Land survey by 30 September 2025 | R0.00 | POE: 1.Appointment Letter | The under-expenditure is due to the non-payment of the service provider following delays in the completion of certain activities that were scheduled for the second quarter. The entity only makes payments for activities that have been verified in accordance with the SLA. The funds will be paid in Quarter 3 once all necessary activities have been completed. | The funds will be paid in Quarter 3 once all necessary activities have been completed in accordance with the SLA.
| 2 | Complete 1 Target: 1.Monitor the undertaking of land surveying by 31 December 2025 | R400 000.00 | POE: 1.Land survey report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Appointment of service provider to conduct Land survey was facilitated by 30 September 2025. the public bid advert closed on 15 September 2025 2. The undertaking of land surveying was not monitored by 30 December 20252 | R158 000.00 | POE: 1.Appointment Letter 2. Land Survey Report | 1 Target achived, 0 Targets not achieved |  | 1 | 1 | 0
Sectiona Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Alfred Nzo Industrial Park
Business Plan Reference | 3.7.2.4
Strategic Objective | Mobilise resources for strategic economic infrastucture initiatives through the establishment of strategic partnerships.
Baseline | Pre- Feasibility undertaken
Annual Output | 1x Full Feasibility study conducted on establishment of industrial Park by 30 June 2026
Budget Amount | R1 200 000.00
Organisational Classification | Local Economic Development / Alfred Nzo Industrial Park
Annual KPI | Number of Draft feasibility studies conducted for the development of industrial Park by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.2.4 | 1 | Complete 1 Target: 1. Develop partnership agreement for the develop a full feasibility study by 30 September 2025 | R500 000.00 | POE: 1. Partnership Agreement | The under-expenditure is due to the non-payment of the service provider following delays in the completion of certain activities that were scheduled for the second quarter. The entity only makes payments for activities that have been verified in accordance with the SLA. The funds will be paid in Quarter 3 once all necessary activities have been completed. | The funds will be paid in Quarter 3 once all necessary activities have been completed in accordance with the SLA.
| 2 | Complete 1 Target: 1. Monitor development of feasibility study by 31 December 2025 | R200 000.00 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Parternship agreement has been developed and was signed with COEGA on 12 August 2025 2.Development of feasibility study was monitored by 31 December 2025 | R0.00 | POE: 1. Partnership Agreement 2. Progress Report | 1 Target achived, 0 targets not achieved |  | 1 | 1 | 0
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Resource Mobilisation
Business Plan Reference | 3.7.2.5
Strategic Objective | Mobilise resources for strategic economic infrastucture initiatives through the establishment of strategic partnerships.
Baseline | Resource Mobilisation Panel
Annual Output | R1 Million secured from 3rd funding by 30 June 2026
Budget Amount | R0.00
Organisational Classification | Enterprise Development and support services / Resource Mobilisation
Annual KPI | Amount of funding secured from 3rd Parties by June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.2.5 | 1 | Complete 1 Target: 1.Develop and submit x 1 funding proposals by 30 September 2025 | R0.00 | POE: 1. Funding proposal | N/A | N/A
| 2 | Complete 1 Target: 1.Develop and submit x 1 funding proposals by 31 December 2025 | R0.00 | POE: 1. Funding Proposal | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Funding proposals were developed and submitted to MerSeta and Bank Seta by 30 September 2025 2. Funding proposals were developed and submitted to LGSETA , Service SETA and W&RSETA by 31 December 2025 | R0.00 | POE: 1. 2 X Funding proposals | 1 Target achived, 0 Targets not achieved |  | 1 | 1 | 0
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Partnerships
Business Plan Reference | 3.7.2.6
Strategic Objective | Mobilise resources for strategic economic infrastucture initiatives through the establishment of strategic partnerships.
Baseline | Signed MoUs
Annual Output | 2x strategic partners secured by June 2026
Budget Amount | R0.00
Organisational Classification | Enterprise Development and support services / Partnerships
Annual KPI | Number of strategic partners secured by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount ( Quarterly) | Quarterly Means of Verification | Reasons for Variance | Corrective Measures
7.2.6 | 1 | Complete 1 Target: 1. Identificaton of strategic partners by 30 September 2025 2. Hold Engagements with strategic partners by 30 September 2025 | R0.00 | POE: 1.Stakeholder Matrix, and Meeting Notes | N/A | N/A
| 2 | Complete 1 Target: 1.Facilitate the drafting of partnership agreement by partners 30 December 2025 | R0.00 | POE: 1. Draft partnership agreement | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Strategic partners have been identified e.g Ntshamathe Communal Property Association and Department of Agriculture 2. Engagments were held with Department of Agriculture and Ntshamathe Communal Property Association. 3.The drafting of partnership agreement by partners was facilitated 30 December 2025 | R0.00 | POE: 1.Stakeholder Matrix, and Meeting Notes 2. Draft partnership agreement | 1 Target achived, 0 Targets not achieved |  | 1 | 1 | 0
[6 empty] | Total | 6 | 5 | 1

## PROGRAMMES
3.7.1 PROGRAMMES DEPARTMENT | [6 empty] | Number of targets | Number of targets | Achieved | Not Achieved
Section Name | Agriculture, Agro-processing and Forestry
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Economic Growth and Development
Business Plan Goal | 1. Sustainable inclusive economic growth 2.Economic infrastructure development
Business Plan Project | Coffee Plantation
Business Plan Reference | 3.7.1.1
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | N/A
Annual Output | One Feasibility Study conducted
Budget Amount | R 600 000,00
Organisational Classification | Agriculture, Agro-processing and Forestry/Coffee Plantation
Annual KPI | Number of Feasibility studies undertaken by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.1 | 1 | Complete 1 Target: 1.Facilitate the appointment of the service provider for the development of feasibiity study by 30 September 2025 | R50 000.00 | POE: 1.Appointment letter | The under-expenditure resulted from delays in the commencement of the project, which only began towards the end of Quarter 2. Consequently, the entity incurred costs relating only to the inception phase of the project | The variance amount will be carried forward to the third quarter and will only be paid upon verification of all deliverables in accordance with the Service Level Agreement (SLA).
| 2 | Complete 1 Target: 1. Hold inception meeting with the service provider by 30 December 2025 2. Monitor progress on development of feasibility study by 30 December 2025 | R200 000.00 | POE: 1.Inception Report 2. Draft feasibility report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.The appointment of the service provider for the development of feasibiity study has been facilitated by 30 September 2025 . Tender advert closed on the 8th september 2025 2. Inception meeting with the service provider was held by 30 December 2025 3. Progress on development of feasibility study was monitored by 30 December 2025 | R110 000.00 | POE: 1.Appointment letter 2. Inception Report 3. Draft feasibilty report | 1 Targets achived, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Amadumbe and Sweet Potato commodity development
Business Plan Reference | 3.7.1.2
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | None
Annual Output | One Feasibility Study conducted
Budget Amount | R 600 000,00
Organisational Classification | Agriculture, Agro-processing and Forestry/Amadumbe and Sweet Potato commodity development
Annual KPI | Number of Feasibility studies undertaken by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.2 | 1 | Complete1 Target : 1.Facilitate the appointment of service provider to conduct feasibility study by 30 September 2025 | R50 000.00 | POE: 1.Appointment letter | The under-expenditure resulted from delays in the commencement of the project, which only began towards the end of Quarter 2. Consequently, the entity incurred costs relating only to the inception phase of the project. | The variance amount will be carried forward to the third quarter and will only be paid upon verification of all deliverables in accordance with the Service Level Agreement (SLA).
| 2 | Complete 1 Target : 1.Hold inception meeting with the Service Provider by December 2025 2. Monitor the developnent of feasibility study by 30 December 2025 | R200 000.00 | POE: 1.Inception Report 2. Draft feasibility study report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.The appointment of the service provider to conduct a feasibilty study has been facilitated by 30 September 2025. Tender advert closed on 08th September 2025. 2. Inception meeting with the service provider was held by 30 December 2025 3. Progress on development of feasibility study was monitored by 30 December 2025 | R110 000.00 | POE: 1. Appointment letter 2. Inception Report 3. Draft feasibilty study report | 1 Targets achieved , 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Emfundisweni Skills Development Centre: Business Support
Business Plan Reference | 3.7.1.3
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | R740 000.00 financial support provided
Annual Output | Non financial and Financial support provided by 30 June 2026
Budget Amount | R2 740 000.00
Organisational Classification | Enterprise Development and support services /Emfundisweni Skills Development Centre: Business Support
Annual KPI | Number of support interventions provided at Emfundiweni by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.3 | 1 | Complete 1 Target: 1. Facilitate the reviewal of Service Level Agreement between Emfundisweni and ANDA by 30 September 2025 2. Development of Business Case for the repurposing of Skills Centre 3. Facilitate payment of operational services by September 2025 4. Monitor progress on social facilitation by September 2025 | R185 000.00 | POE: 1. Signed SLA 2. Business Case 3. Proof of payment 4. Social Facilitation progress report | The over-expenditure resulted from the payment of casual workers providing cleaning services at the centre. These workers were back-paid for services rendered in the previous quarters, which led to the over-expenditure recorded in the current quarter. | None, Because annual budget has not been exceeded. The over expenditure will be cancelled by a positive annual budget that has not been exceeded. Therefore in overall the expenditure is still within the annual budgeted forecasts.
| 2 | Complete 1 Target: 1. Monitor progress on social facilitation by 30 December 2025 2.Facilitate the payment operations servises by 30 December 2025 | R185 000.00 | POE: 1. Social Facilitation progress report 2. Proof of payment 3. Partnership agreement
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Service Level Agreement has been reviewed and signed by 30 September 2025 2. Emfundisweni business case for repurposing of Emfundisweni has been developed by 30 September 2025. 3. Payment of operational services has been faciliated e.g electricity costs by 30 September 2025. 4. Progress on social facilitation has been monitored by 30 September 2025. 5. Progress on social facilitation was monitored by 30 December 2025 6. Payment operation services were facilitated by 30 December 2025 | R376 055.64 | POE: 1. Signed SLA 2. Business Case 3. Proof of payment 4. Social Facilitation progress report 5. Partnership agreement | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Local Economic Development
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Fresh Produce Industry Development
Business Plan Reference | 3.7.1.4
Strategic Objective | To be recognised as the food basket of the region and markets beyond
Baseline | 1x Trade Fair event hosted at Winnie Madikizela Mandela LM
Annual Output | 2 x Trade fairs held by June 2026
Budget Amount | R500 000.00
Organisational Classification | Enterprise Development and support services / Fresh Produce Industry Produce
Annual KPI | Number of Trade Fairs held, and business plans developed by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.4 | 1 | Complete1 Target : 1. Submit Monitor progress on development of business plans by 30 September 2025 | R200 000.00 | POE: 1. Business plans develoment Progress Reports | The over-expenditure resulted from the payment of activities that were completed in the previous quarter but were only paid in the current quarter following the completion of the verification process | None, Because annual budget has not been exceeded. The over expenditure will be cancelled by a positive annual budget that has not been exceeded. Therefore in overall the expenditure is still within the annual budgeted forecasts.
| 2 | Complete 1 Target : 1.Finalise the development of 2x business plans by 30 December 2025 | R200 000.00 | POE: 1.Business plans Reports
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on the development of business plans has been monitored by 30 September 2025, Progress report has been submitted 2. Development of 2x business plans was finalized by 30 December 2025 | R499 936.30 | POE: 1. Business plans development Progress Reports 2. Business Plan Reports | 1 Targets achieved, 0 Targets not achieved
[7 empty] | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | SETA Accreditation
Business Plan Reference | 3.7.1.5
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | Appointment of service provider
Annual Output | 1x full SETA accreditation secured by 30 June 2026
Budget Amount | 200000
Organisational Classification | Enterprise Development and support services /SETA accreditation
Annual KPI | Number of SETA accreditations secured by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.5 | 1 | Complete 1 Target: Monitor progress on application for ANDA SETA accreditation by 30 September 2025 | R 66 668.00 | POE: 1. Progress Report | The under-expenditure resulted from delays in the implementation of the project, which led to certain activities not being fully completed by the end of Quarter 2. Consequently, the entity incurred expenditure only for activities that could be verified in accordance with the Service Level Agreement (SLA). | The variance will be carried forward to the third quarter and will be paid once all activities have been completed and verified in accordance with the Service Level Agreement (SLA).
| 2 | Complete 1 Target: Monitor progress on application for ANDA SETA accreditation by 30 December 2025 | R 66 666.00 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) |  | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on application for ANDA Seta Accreditation has been monitored. QCTO application for first phase has been completed 2. Progress on application for ANDA SETA accreditation was monitored by 30 December 2025 | R60 000.00 | POE: 1.Progress Report | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA: Learnership (Generic Management)
Business Plan Reference | 3.7.1.6
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | 1x Learnership programme implemented for 29 Unemployed leaners on generic Management
Annual Output | Issuing of certificates and payment of the last tranche to the SDP
Budget Amount | 76220
Organisational Classification | Enterprise Development and support services /Services SETA: Learnership (Generic Management)
Annual KPI | Number of certificates issued for generic management learnership by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.6 | 1 | Complete 1 Target: 1. Handover certificates to 15 competent learners by 30 September 2025 2. Faciliate the payment of last tranche to the 1x Skills provider by 30 September 2025 | R176 220.000 | POE: 1. Certificates 2. Proof of payment | Certifates could not be received due to the backlog that Service Seta is experiencing. Due to non receipt of certificates payment of last tranch was not processed. | Certificates will be received in the 3rd quarter of 2025/26 financial year. Payment of last tranche will be facilitated in Q3 of 2025/26/FY.
| 2 | None | None | None
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Certificates have not been handed over to 15 competent learners by 30 September 2025 2. The payment of last tranche to 1x Skills provider has not yet been facilitated and finalised by 30 September 2025 | R0.00 | None | 0 Targets achieved, 1 Target not achieved |  | 2 | 1 | 0 | 1
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA : Leanership Programme(Business Administration Services)
Business Plan Reference | 3.7.1.7
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | 1x Learnership programmes implemented for 47 leaners in Business Administration Services
Annual Output | Issuing of certificates and payment of the last tranche to the SDP
Budget Amount | 73063
Organisational Classification | Enterprise Development and support services /Services SETA : Leanership Programme(Business Administration Services)
Annual KPI | Number of certificates issued for Business Admin learnership by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.7 | 1 | Complete 1 Target: 1. Handover Busines Admin certificates to 25 competent learners by 30 September 2025 2. Faciliate the payment of last tranche to the 1x Skills provider by 30 September 2025 | 73062.5 | POE: 1. Certificates 2. Proof of payment | Certifates could not be received due to the backlog that Service Seta is experiencing. Due to non receipt of certificates payment of last tranch was not processed. | Certificates will be received inthe 2nd quarter of 2025/26 financial year. Payment of last tranche will be facilitated in Q2 of 2025/26/FY.
| 2 | N/A | N/A | N/A
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. Busines Admin certificates have not been handed over to 25 competent learners by 30 September 2025 2. Payment of last tranche to the 1x Skills provider could not be facilitated by 30 September 2025 | R0.00 | None | 0 Targets achieved, 1 Target not achieved |  | 2 | 1 | 0 | 1
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA : Leanership Programme (Clothing Manufacturing processes)
Business Plan Reference | 3.7.1.8
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | 1x Learnership programmes implemented for 22 leaners
Annual Output | Issuing of certificates and payment of the last tranche to the SDP
Budget Amount | (R322 500.00)
Organisational Classification | Enterprise Development and support services /Services SETA : Leanership Programme (Sewing)
Annual KPI | Number of certificates issued for clothing manufacturing learnership by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.8 | 1 | Complete 1 Target: 1. Undertake external moderation by 30 September 2025 | R161 250.00 | POE: 1. Moderation Report | The under-expenditure resulted from the closure report not yet being submitted, which delayed the processing of the final payment | The variance will be carried forward to the third quarter and will be paid once the closure report has been submitted and verified.
| 2 | Complete 1 Target: 1. Handover 15x clothing manufacturing certificates to 15 competent learners by 30 December 2025 2. Faciliate the payment of last tranche to the 1x Skills provider by 30 December 2025 | R161 250.00 | POE: 1. Certificates 2. Proof of payment
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1. External moderation was undertaken by 30 September 2025 2. 15 learners received 15x clothing manufacturing certificates by 30 December 2025 3. Payment of last trance to the 1x Skills provider was facilitated by 31 December 2025 | R152 000.00 | POE: 1. Moderation Report 2. Certicates 3. Proof of payment | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Foodbev: Leanership Programme
Business Plan Reference | 3.7.1.9
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1X learnership programme implemented for 68 participants on Bread and Flour Confectionery Baking
Budget Amount | 1125600
Organisational Classification | Enterprise Development and support services /Foodbev: Leanership Programme
Annual KPI | Number of Bread and Flour Confectionery Learnership programme implemented 68 unemployed learners by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.9 | 1 | Complete 1 Target: 1. Monitor progress on the implementation of 1 learnership programme by 30 September 2025 | R600 000.00 | POE: 1. Progress Report | The under-expenditure is due to the non-payment of the service provider, following delays in the receipt of certificates. | The variance will be paid in the third quarter once the outstanding certificates have been received.
| 2 | Complete 1 Target: Finalise and close up 1 learnership programme by 30 December 2025 | 525600 | POE: 1.Closure Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on implemention of the learnership programmes has been monitored. Workplace practical training has been completed and stipends were paid to all active learners 2. 1 learnership programme was finalised and closed up by 31 December 2025 | R476 000.00 | POE: 1. Progress Report 2 Closure Report | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Leanership Programme Local Economic Development
Business Plan Reference | 3.7.1.10
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 20 leaners in economic development (LGSETA)
Budget Amount | R300 810.00
Organisational Classification | Enterprise Development and support services /Services SETA: Leanership Programme economic development (LGSETA)
Annual KPI | Number of Learnership programme implemented for 14 learners on Local Economic Development by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.10 | 1 | Complete 1 Target: 1. Monitor progress on implementation of 1 learnership programme by 30 September 2025 | R75 202.50 | POE: 1. Progress Report | The over-expenditure is due to payments for last quarter's activities, which were only fully completed in the current quarter and therefore had to be charged to the current quarter's budget. | None, Because annual budget has not been exceeded. The over expenditure will be cancelled by a positive annual budget that has not been exceeded. Therefore in overall the expenditure is still within the annual budgeted forecasts.
| 2 | Complete 1 Target: 1. Monitor progress on implementation of 1 learnership programme by 30 December 2025 | R75 202.50 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on implementation of 1 learnner programme has been monitored by 30 September 2025. 15 units standards have been covered and all active learners have been registered on LGSETA system. 2. Progress on implementation of 1 learnership programme was monitored by 31 December 2025 | R179 975.00 | POE: 1.Progress Report | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA : Leanership Programme enviromental practice
Business Plan Reference | 3.7.1.11
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 17 employed leaners on environmental practise
Budget Amount | R240 700.00
Organisational Classification | Enterprise Development and support services / LGSETA : Leanership Programme enviromental practice
Annual KPI | Number of Learnership programmes implemented on Environmental Practice by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.11 | 1 | Complete 1 Target: 1. Monitor Progress on implementation of 1 learnership programme by 30 September 2025 | R60 175.00 | POE: 1. Progress Report | The over-expenditure is due to payments for last quarter's activities, which were only fully completed in the current quarter and therefore had to be charged to the current quarter's budget. | None, Because annual budget has not been exceeded. The over expenditure will be cancelled by a positive annual budget that has not been exceeded. Therefore in overall the expenditure is still within the annual budgeted forecasts.
| 2 | Complete 1 Target: 1.Monitor Progress on implementation of 1 learnership programme by 30 December 2025 | R60 175.00 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on implementation of 1 learnership programmes has been monitored by 30 September 2025, 90% of training has been conducted as only 4 unit standards are still outstanding. 2. Progress on implementation of 1 learnership programme was monitored by 31 December 2025 | R150 075.00 | POE: 1. Progress Report | 1 Target achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Artisan Recognition of Prior Learning(ARPL) on Plumbing
Business Plan Reference | 3.7.1.12
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x ARPL programmes implemented for 49 employed leaners on plumbing
Budget Amount | R514 500.00
Organisational Classification | Enterprise Development and support services / LGSETA: ARPL on Plumbing
Annual KPI | Number of ARPL programme implemented on plumbing for 48 learners by June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.12 | 1 | Complete 1 Target: 1. Monitor progress on implementation of 1 ARPL programme by 30 September 2025 | R171 500.00 | POE: 1. Progress Report | The under-expenditure is due to the non-payment of the service provider. Twenty-four learners have completed trade testing; however, an additional 22 learners were supposed to undergo gap training by December, which was rescheduled to January 2026. | Expenditure will be incurred once the additional 22 learners undergo gap training in the third quarter.
| 2 | Complete 1 Target: 1. Monitor progress on implementation of 1 ARPL programme by 30 December 2025 | R171 500.00 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1Target: 1.Progress on implementation of 1 ARPL programme has been monitored by 30 September 2025, 24 learners have completed trade testing, additional 22 learners are preparing to undergo gap training by 30 December 2025 2. Progress on implementation of 1 ARPL programme was monitored by 31 December 2025 | 34929 | POE: 1.Progress Report | 1 Target achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Artisan Recognition of Prior Learning(ARPL) Programme (bricklaying)
Business Plan Reference | 3.7.1.13
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x ARPL programmes implemented for 05 employed leaners on Bricklaying
Budget Amount | R175 000.00
Organisational Classification | Enterprise Development and support services / LGSETA: ARPL on Bricklaying
Annual KPI | Number ARPL programmes implemented on Bricklaying for 5 learners by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.13 | 1 | Complete 1 Target: 1. Monitor progress on implementation of 1 ARPL programme by 30 September 2025 | R58 333.00 | POE: 1. Progress Report | The under-expenditure is due to the non-payment of the service provider following delays in the commencement of the project. The entity only makes payments for activities that have been verified in terms of the Service Level Agreement (SLA). | The funds will be paid in Quarter 3 once all necessary activities have been completed in accordance with the SLA.
| 2 | Complete 1 Target: 1. Monitor progress on implementation of 1 ARPL programme by 30 December 2025 | R58 333.00 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on implementation of 1 ARPL programme has been monitored by 30 Septemebr 2025, learners are currently undergoing gap training before the trade testing. 2. Progress on implementation of 1 ARPL programme was monitored by 31 December 2025 | R0.00 | POE: 1.Progress Report | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | LGSETA: Apprenticeship Programme (Plumbing)
Business Plan Reference | 3.7.1.14
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Learnership programmes implemented for 11 Unemployed leaners on plumbing
Budget Amount | R2 191 285.00
Organisational Classification | Enterprise Development and support services / LGSETA: Apprenticeship on plumbing
Annual KPI | Number of Apprenticeship programmes by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.14 | 1 | Complete 1 Target: 1. Monitor Progress on implementation of 1 apprenticeship programme by 30 September 2025 | R547 821.00 | POE: 1. Progress Report | The under-expenditure is due to the non-payment of the service provider following delays in the completion of certain activities that were scheduled for the second quarter. The entity only makes payments for activities that have been verified in accordance with the SLA. | The funds will be paid in Quarter 3 once all necessary activities have been completed in accordance with the SLA.
| 2 | Complete 1 Target: 1. Monitor progress on implementation of 1 apprenticeship programme by 30 December 2025 | R547 821.00 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | 1.Progress on implementation of 1 apprenticeship programme has been monitored by 30 September 2025, learners have recieved protective clothing and they are placed at ANDM water division for practical training 2. Progress on implementation of 1 apprenticehip programme was monitored by 31 December 2025 | R547 821.00 | POE: 1. Progress Report | 1 Target achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and suport services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Services SETA: NATED internship programme
Business Plan Reference | 3.7.1.15
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Nated internship Programme for 59 unemployed learners implemented.
Budget Amount | R354 000.00
Organisational Classification | Enterprise Development and support services / Services SETA: NATED internship programme
Annual KPI | Number of Nated Internship programme implemented by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.15 | 1 | Complete 1 Target: 1.Monitor progress on the implementation Nated Internship Programme by 30 September 2025 | R177 000.00 | POE: 1. Progress Report | The under-expenditure is due to the project having been closed and completed | The variance will be addressed in the mid-year adjustment.
| 2 | Complete 1 Target: 1. Finalise and close up 1x Nated Internship Programme by 30 December 2025 | R177 000.00 | POE: 1.Closure Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on implementaton of Nated Intenship programme has been monitored by 30 September 2025. Learners have completed the intenship programme on 30 August 2025, stipends were paid to all active learners 2. 1x Nated Internship Programme was finalised and closed up by 31 Decmber 2025 | R342 000.00 | POE: 1. Progress Report 2. Closure Report | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
Department | PROGRAMMES
Section Name | Enterprise Development and support services
National KPA | Local Economic Development
IDP Goal (s) | Inclusive Growth and Development
Business Plan Goal | 1.Sustainable inclusive growth and development 2. Economic Infrastructure Development
Business Plan Project | Construction Seta: Internship Programme
Business Plan Reference | 3.7.1.16
Strategic Objective | Increase the contribution of small enterprises to the growth of the ANDM economy and transfer skills to the unemployed
Baseline | None
Annual Output | 1x Internship programme implemented for 15 Interns
Budget Amount | R420 000.00
Organisational Classification | Enterprise Development and support services / Construction Seta : Internship Programme
Annual KPI | Number of Internship programme implemented for unemployed learners by 30 June 2026
SDBIP Reference | Quarter | Quarterly Targets | Amount (Quarterly) | Quarterly (Means of Verification) | Reason for variance | Corrective Action
7.1.16 | 1 | Complete 1 Target : 1. Monitor progress on the implementation of internship programme by 30 September 2025 | R105 000 | POE: 1. Progress Report | The over-expenditure is due to payments for learners who were incorrectly reported as having withdrawn from the training but subsequently returned to continue with the programme. | None, Because annual budget has not been exceeded. The over expenditure will be cancelled by a positive annual budget that has not been exceeded. Therefore in overall the expenditure is still within the annual budgeted forecasts.
| 2 | Complete 1 Target : 1. Monitor progress on the implementation of internship programme by 30 December 2025 | R105 000 | POE: 1. Progress Report
| Period of reporting | Actual Mid-year Target Achieved | Actual Amount Expenditure (Mid-year) | Actual Means of verification | Number of Targets Achieved & Not achieved
| Midterm | Completed 1 Target: 1.Progress on implementation of intenship programme has been monitored by 30 September 2025, learners are located in various construction sites across the District doing practical work. 2. Progress on the implementation of internship programme was monitored by 31 Decmber 2025 | R360 000.00 | POE: 1.Progress Report | 1 Targets achieved, 0 Targets not achieved |  | 2 | 1 | 1 | 0
[6 empty] | Total | 32 | 16 | 14 | 2